## Note
Strategic Equality Plan - Action Plan 2024 - 2028
Please Note: Some actions will be relevant under more than one objective but will only be shown once on the Action Plan under the most relevant heading. Between 2024 and 2028, we anticipate that the financial constraints placed upon Conwy County Borough Council, along with all other public bodies in Wales, will be even greater than they have been in the previous 4 years. Whilst what we have set out in the Action Plan attached to our revised Strategic Equality Plan is believed to be achievable at the time of writing, we will review this action plan annually to prioritise and reprioritise what we do to survive these ever increasing pressures.
Mae’r ddogfen hon ar gael yn Gymraeg hefyd

## 2024-2028 Actions
Objective | Priority Area | # | Action | Source / Related Plan(s) | Responsibility | Race | Disability | Sex | Gender Reassignment | Sexual Orientation | Age | Religion/Belief | Marriage / Civil Partnership | Pregnancy / Maternity | Complete by
Objective 1: Outcomes in education learning and wellbeing are improved | Priority Area 1.1: All children and young people attend schools regularly and achieve their learning potential | 1 | Implement the Additional Learning Needs (ALN) Act to ensure that all learners with ALN (aged 0-25) are supported to overcome barriers to learning and achieve their full potential | Corporate Plan 2022-2027 | Education |  | ü |  |  |  | ü |  |  |  | 2027-03-31
Objective 1: Outcomes in education learning and wellbeing are improved | Priority Area 1.1: All children and young people attend schools regularly and achieve their learning potential | 2 | Implement the updated guidance on Exclusion from Schools and Pupil Referral Units in relation to learners who we are aware can be disproportionately subject to permanent or temporary exclusions; this includes, but is not limited to ethnic minority learners and learners with special educational needs, so that exclusions don’t disproportionately impact specific groups |  | Education | ü | ü | ü | ü | ü | ü | ü |  |  | Review March 2025
Objective 1: Outcomes in education learning and wellbeing are improved | Priority Area 1.1: All children and young people attend schools regularly and achieve their learning potential | 3 | Support schools in the implementation of the updated statutory Gypsies, Roma and Travellers’ guidance for schools (when published) | Anti-racist Wales Action Plan | Education | ü |  |  |  |  | ü |  |  |  | Review March 2025
Objective 1: Outcomes in education learning and wellbeing are improved | Priority Area 1.1: All children and young people attend schools regularly and achieve their learning potential | 4 | Work in partnership with Conwy schools and partners to implement the revised ‘Rights, Respect, Equality’ All Wales Anti-Bullying Guidance providing relevant advice and guidance | Anti-racist Wales Action Plan / LGBTQ+ Action Plan | Education | ü | ü | ü | ü | ü | ü | ü |  | ü | Review March 2025
Objective 1: Outcomes in education learning and wellbeing are improved | Priority Area 1.1: All children and young people attend schools regularly and achieve their learning potential | 5 | Support schools with the implementation of Welsh Government's Transgender Guidance for schools | LGBTQ+ Action Plan | Education |  |  |  | ü |  | ü |  |  |  | Review July 2024
Objective 1: Outcomes in education learning and wellbeing are improved | Priority Area 1.1: All children and young people attend schools regularly and achieve their learning potential | 6 | We will ensure schools in Conwy publish Strategic Equality Plans and Equality Objectives, and will introduce a consistent assessment of School Equality Plans |  | Education | ü | ü | ü | ü | ü | ü | ü |  | ü | Review March 2025
Objective 1: Outcomes in education learning and wellbeing are improved | Priority Area 1.1: All children and young people attend schools regularly and achieve their learning potential | 7 | Work with GwE to ensure that schools when producing their School Development Plans meet the requirements of the Public Sector Equality Duty including annual reporting on progress |  | Education | ü | ü | ü | ü | ü | ü | ü |  | ü | Review December 2024
Objective 1: Outcomes in education learning and wellbeing are improved | Priority Area 1.1: All children and young people attend schools regularly and achieve their learning potential | 8 | Promoting and further developing Welsh medium education whilst encouraging children and young people to be proud of the Welsh language, its heritage and culture | Corporate Plan 2022-2027 | Education | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2027-03-31
Objective 1: Outcomes in education learning and wellbeing are improved | Priority Area 1.1: All children and young people attend schools regularly and achieve their learning potential | 9 | Analyse data on Black, Asian and Minority Ethnic people that attend Welsh-medium education to develop local strategies to increase this number and tackle the barriers to accessing Welsh-medium education | Anti-racist Wales Action Plan | Education | ü |  |  |  |  | ü
Objective 1: Outcomes in education learning and wellbeing are improved | Priority Area 1.2: Children and young people educated in childcare settings through to early education achieve their learning potential | 10 | We will engage with Black, Asian and Minority Ethnic communities to identify how the voice and lived experiences of people in these communities can be better captured as part of the Childcare Sufficiency Assessment that Local Authorities are required to undertake to improve access to childcare and play settings as well as access to play opportunities | Anti-racist Wales Action Plan | Education | ü |  |  |  |  | ü
Objective 1: Outcomes in education learning and wellbeing are improved | Priority Area 1.2: Children and young people educated in childcare settings through to early education achieve their learning potential | 11 | To comply with Welsh Government’s target to offer funded part-time early education places for children from the term following their 3rd birthday within local authority approved voluntary and private sector non-maintained settings |  | Education | [5 empty] | ü |  |  |  | 2025-03-31
Objective 1: Outcomes in education learning and wellbeing are improved | Priority Area 1.3: Children and young people are safe and feel safe at school, have equal opportunities, and are encouraged to live a healthy lifestyle | 12 | Support schools to introduce the framework on embedding a whole school approach to emotional and mental wellbeing |  | Education |  | ü |  |  |  | ü
Objective 1: Outcomes in education learning and wellbeing are improved | Priority Area 1.3: Children and young people are safe and feel safe at school, have equal opportunities, and are encouraged to live a healthy lifestyle | 13 | Support schools with the implementation of Welsh Government’s revised statutory guidance for schools in respect of wellbeing, recognising the particular needs of learners from an ethnic minority backgrounds | Anti-racist Wales Action Plan | Education | ü |  |  |  |  | ü
Objective 1: Outcomes in education learning and wellbeing are improved | Priority Area 1.3: Children and young people are safe and feel safe at school, have equal opportunities, and are encouraged to live a healthy lifestyle | 14 | Support schools and their localities to deliver the principles set out in the 5 Ways to Wellbeing |  | Education | ü | ü | ü | ü | ü | ü | ü |  | ü
Objective 1: Outcomes in education learning and wellbeing are improved | Priority Area 1.3: Children and young people are safe and feel safe at school, have equal opportunities, and are encouraged to live a healthy lifestyle | 15 | Support children, young people and their families to access education and community-based activities | Corporate Plan 2022-2027 | Education | ü | ü | ü | ü | ü | ü | ü |  | ü | 2027-03-31
Objective 1: Outcomes in education learning and wellbeing are improved | Priority Area 1.3: Children and young people are safe and feel safe at school, have equal opportunities, and are encouraged to live a healthy lifestyle | 16 | Source funding to support schools to deliver a broad and balanced range of activities (e.g. Road Safety / Bikeability Cycle Safety Scheme, SEN Projects) |  | Economy & Culture | ü | ü | ü | ü | ü | ü | ü |  | ü | Ongoing
Objective 1: Outcomes in education learning and wellbeing are improved | Priority Area 1.3: Children and young people are safe and feel safe at school, have equal opportunities, and are encouraged to live a healthy lifestyle | 17 | Pilot a Junior Fitness Officer role to engage with high school pupils about the Junior Ffit Conwy Membership and the benefits of exercise |  | Economy & Culture | ü | ü | ü | ü | ü | ü | ü |  | ü | 2024-12-31
Objective 1: Outcomes in education learning and wellbeing are improved | Priority Area 1.4: To support young people to become positive role models within their communities and society | 18 | Improve access to Youth Work provision and safe spaces for young people with differing backgrounds and needs, including LGBTQ+ young people, and increased diversity within the youth work workforce. | LGBTQ+ Action Plan | Education | ü | ü | ü | ü | ü | ü | ü |  | ü | Ongoing
Objective 1: Outcomes in education learning and wellbeing are improved | Priority Area 1.4: To support young people to become positive role models within their communities and society | 19 | Develop partnerships with voluntary organisations to increase the offer of youth work through the medium of Welsh in rural communities. |  | Education | ü |  |  |  |  | ü
Objective 1: Outcomes in education learning and wellbeing are improved | Priority Area 1.5: To support everyone under the age of 25 to access an offer of work, education, training, or self-employment | 20 | We will develop a framework for employability projects and initiatives within the Youth Service, responding to the substantial increase in the WG Youth Support Grant, developing and implementing a range of initiatives in partnership with Education (Education and Progression Co-ordinator and Housing) |  | Education | ü | ü | ü | ü | ü | ü | ü | ü | ü
Objective 1: Outcomes in education learning and wellbeing are improved | Priority Area 1.5: To support everyone under the age of 25 to access an offer of work, education, training, or self-employment | 21 | Ensure that young people have a good awareness of employment opportunities and the appropriate skills to access the world of work | Corporate Plan 2022-2027 | Education | ü | ü | ü | ü | ü | ü | ü |  | ü | 2027-03-31
Objective 2: We will take action to ensure we are an equal opportunities employer and reduce pay gaps | Priority Area 2.1: Address gender, ethnicity and disability pay differences | 22 | Continue to undertake Equal Pay Audits periodically and continue to report pay gaps for gender, ethnicity, disability and age in SEP Annual Reports - taking steps to identify and implement actions where there are gaps above 5% in line with EHRC guidance |  | People and Performance | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2027-03-31
Objective 2: We will take action to ensure we are an equal opportunities employer and reduce pay gaps | Priority Area 2.1: Address gender, ethnicity and disability pay differences | 23 | When the next Staff Survey is carried out, include a section to seek feedback around the pay gap and job segregation issues, and questions relevant to a safe and inclusive work environment to ascertain if staff feel empowered to challenge discriminatory practice. Actions identified will be included in the annual review of this plan | Anti-racist Wales Action Plan | People and Performance | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2025-03-31
Objective 2: We will take action to ensure we are an equal opportunities employer and reduce pay gaps | Priority Area 2.1: Address gender, ethnicity and disability pay differences | 24 | Review and embed our Job Evaluation Policy and Procedures | People Strategy 2022-2027 | People and Performance | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2024-12-01
Objective 2: We will take action to ensure we are an equal opportunities employer and reduce pay gaps | Priority Area 2.2: Review our (flexible) working practices to ensure equal opportunities at all levels | 25 | Further review and reflect on our approach to flexible working practices through the staff survey to ensure it continues to deliver equal opportunities across the whole organisation | Anti-racist Wales Action Plan / People Strategy 2022-2027 | People and Performance | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2025-03-31
Objective 2: We will take action to ensure we are an equal opportunities employer and reduce pay gaps | Priority Area 2.3: Ensure effective policies to prevent and respond to sexual harassment and other forms of harassment | 26 | Review our current Harassment Policy to ensure it sufficiently deals with the subject of Sexual Harassment, and other forms of harassment, ensuring a support mechanism is included for victims. |  | People and Performance | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2024-12-31
Objective 2: We will take action to ensure we are an equal opportunities employer and reduce pay gaps | Priority Area 2.3: Ensure effective policies to prevent and respond to sexual harassment and other forms of harassment | 27 | Provide training for managers on handling harassment allegations, referring to the TUC Sexual Harassment in the Workplace Toolkit, with implementation of revised policy |  | People and Performance | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2025-03-31
Objective 2: We will take action to ensure we are an equal opportunities employer and reduce pay gaps | Priority Area 2.3: Ensure effective policies to prevent and respond to sexual harassment and other forms of harassment | 28 | Review our Grievance Policy to ensure it sufficiently deals with the subject of Sexual Harassment allegations |  | People and Performance | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2024-12-31
Objective 2: We will take action to ensure we are an equal opportunities employer and reduce pay gaps | Priority Area 2.4: Increase the number of disabled people in work | 29 | Develop an action plan to work towards Disability Confident Leader status |  | People and Performance | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2025-09-30
Objective 2: We will take action to ensure we are an equal opportunities employer and reduce pay gaps | Priority Area 2.4: Increase the number of disabled people in work | 30 | Undertake consultation to consider if it would be appropriate to introduce a Workplace Adjustments Passport |  | People and Performance | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2024-12-31
Objective 2: We will take action to ensure we are an equal opportunities employer and reduce pay gaps | Priority Area 2.4: Increase the number of disabled people in work | 31 | Provide written feedback for disabled applicants who don’t get shortlisted or employed to explain why and explain the process (provide training for managers) |  | All Services | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 2: We will take action to ensure we are an equal opportunities employer and reduce pay gaps | Priority Area 2.4: Increase the number of disabled people in work | 32 | Review options for sharing vacancies with different equality groups and organisations |  | People and Performance | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2025-03-31
Objective 2: We will take action to ensure we are an equal opportunities employer and reduce pay gaps | Priority Area 2.4: Increase the number of disabled people in work | 33 | Develop disability supported employment services, including via an Employment Pathway Co-ordinator role |  | Social Care - Disability Service |  | ü | [7 empty] | Ongoing
Objective 2: We will take action to ensure we are an equal opportunities employer and reduce pay gaps | Priority Area 2.5: Reduce gender segregation (the unequal distribution of men and women working in traditionally gender specific roles) | 34 | Implement actions from the Equal Pay Audit 2018-2023 to seek to influence gender segregation in specific service areas |  | People & Performance |  |  | ü | [6 empty] | 2025-03-31
Objective 2: We will take action to ensure we are an equal opportunities employer and reduce pay gaps | Priority Area 2.6: Improve participation of women, ethnic minorities and disabled people across apprenticeships | 35 | Promote opportunities for work placements, work experience and apprenticeships to stakeholders who represent people from different Protected Characteristics particularly where under-represented |  | All Services | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 2: We will take action to ensure we are an equal opportunities employer and reduce pay gaps | Priority Area 2.6: Improve participation of women, ethnic minorities and disabled people across apprenticeships | 36 | Explore how we collect and interogate equality data from work placement applications and successful placements |  | People and Performance | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2025-03-31
Objective 2: We will take action to ensure we are an equal opportunities employer and reduce pay gaps | Priority Area 2.6: Improve participation of women, ethnic minorities and disabled people across apprenticeships | 37 | Work with Children, Families and Safeguarding to promote appropriate initiatives within the council to develop employment pathways for our Children Looked After |  | People and Performance / Social Care | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 2: We will take action to ensure we are an equal opportunities employer and reduce pay gaps | Priority Area 2.7: Consider the use of positive action measures in recruitment campaigns where specific groups are under-represented | 38 | Produce and implement guidance on positive action so that managers can work towards a workforce that more closely reflects the makeup of the local community, ensuring that policy training content is updated to promote and incorporate positive action opportunities | Anti-racist Wales Action Plan / LGBTQ+ Action Plan | People and Performance | ü | ü | ü | ü | ü | ü |  |  |  | 2024-12-31
Objective 2: We will take action to ensure we are an equal opportunities employer and reduce pay gaps | Priority Area 2.7: Consider the use of positive action measures in recruitment campaigns where specific groups are under-represented | 39 | Ensure that positive action measures are considered, promoted and implemented, where applicable, with the objective of making our workforce more closely reflect the makeup of the local community | Anti-racist Wales Action Plan | All Services | ü | ü | ü | ü | ü | ü |  |  |  | Ongoing
Objective 2: We will take action to ensure we are an equal opportunities employer and reduce pay gaps | Priority Area 2.7: Consider the use of positive action measures in recruitment campaigns where specific groups are under-represented | 40 | Using equality monitoring information during the workforce planning process we will review training and development opportunities for under-represented groups at senior levels (circa G09 and above) within the workforce with a view to equipping them for internal progression |  | People and Performance | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2026-03-31
Objective 2: We will take action to ensure we are an equal opportunities employer and reduce pay gaps | Priority Area 2.8: Implement a programme of anti-racism and anti-discrimination within the organisation, promoting the value of positive relationships, diversity and inclusion | 41 | Create a checklist to enable policy authors to review all employment policies through an anti-discriminatory and zero tolerance lens when developing and reviewing employment policies | Anti-racist Wales Action Plan | People and Performance | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2024-12-31
Objective 2: We will take action to ensure we are an equal opportunities employer and reduce pay gaps | Priority Area 2.8: Implement a programme of anti-racism and anti-discrimination within the organisation, promoting the value of positive relationships, diversity and inclusion | 42 | Review training provision on equality and diversity to ensure it delivers on the anti-discrimination agenda and a zero tolerance approach (not just non-discrimination) preferably involving trainers with lived experience (utilising Academi Wales' Leadership Behaviours Framework which is currently being developed) | Anti-racist Wales Action Plan | People and Performance | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/03/2025 and ongoing
Objective 2: We will take action to ensure we are an equal opportunities employer and reduce pay gaps | Priority Area 2.8: Implement a programme of anti-racism and anti-discrimination within the organisation, promoting the value of positive relationships, diversity and inclusion | 43 | Monitor discrimination, harassment, bullying and grievance cases through the Employment Monitoring Report and Exit Interviews via dashboard data to identify any discriminatory practice and introduce preventative measures and develop opportunities for learning as appropriate | Anti-racist Wales Action Plan | People and Performance | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 2: We will take action to ensure we are an equal opportunities employer and reduce pay gaps | Priority Area 2.8: Implement a programme of anti-racism and anti-discrimination within the organisation, promoting the value of positive relationships, diversity and inclusion | 44 | Develop and implement a Transgender Policy | LGBTQ+ Action Plan | People and Performance | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2025-03-31
Objective 2: We will take action to ensure we are an equal opportunities employer and reduce pay gaps | Priority Area 2.8: Implement a programme of anti-racism and anti-discrimination within the organisation, promoting the value of positive relationships, diversity and inclusion | 45 | Create and roll out LGBTQ+ and Gender Identity Guidance for employment and service delivery, to demonstrate recognition of non-binary and intersex people in our policies, practices and data collection systems | LGBTQ+ Action Plan | People and Performance |  |  |  | ü | ü |  |  |  |  | 2025-03-31
Objective 2: We will take action to ensure we are an equal opportunities employer and reduce pay gaps | Priority Area 2.8: Implement a programme of anti-racism and anti-discrimination within the organisation, promoting the value of positive relationships, diversity and inclusion | 46 | Subject to funding, consider reviewing our cultural competency position via Diverse Cymru's Cultural Competence Certification Scheme | Anti-racist Action Plan | People and Performance | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2026-03-31
Objective 2: We will take action to ensure we are an equal opportunities employer and reduce pay gaps | Priority Area 2.9: Address the barriers to employment for diverse communities | 47 | Implement actions identified from engagement work carried out around Empowering Diverse Communities into Employment, for ethnic minority and other minority groups, to reduce barriers to employment | Anti-racist Action Plan / LGBTQ+ Action Plan | People and Performance | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/03/2025 and ongoing
Objective 2: We will take action to ensure we are an equal opportunities employer and reduce pay gaps | Priority Area 2.9: Address the barriers to employment for diverse communities | 48 | Subject to funding, develop policy awareness raising communications for managers and signpost to sources of information and guidance about workforce rights and employer and employee responsibilities | Anti-racist Wales Action Plan | People and Performance | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 2: We will take action to ensure we are an equal opportunities employer and reduce pay gaps | Priority Area 2.9: Address the barriers to employment for diverse communities | 49 | Continue to anonymise applicant details prior to shortlisting and review how this can be improved to ensure any biases to the recruitment process are minimised | Anti-racist Wales Action Plan | People and Performance | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 2: We will take action to ensure we are an equal opportunities employer and reduce pay gaps | Priority Area 2.9: Address the barriers to employment for diverse communities | 50 | Encourage other employers who we commission work to, to adopt fair and transparent recruitment practices to remove bias about protected characteristics | Anti-racist Wales Action Plan | People and Performance / Social Care | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 2: We will take action to ensure we are an equal opportunities employer and reduce pay gaps | Other actions on Employment identified from consultation | 51 | Review and revise the Corporate Policies for Maternity, Breastfeeding and Adoption into a combined policy, also incorporating Shared Parental Leave, to ensure they are relevant and up to date in respect of legislation and implement the 6 areas of action outlined in “Pregnancy and Maternity Discrimination in the workplace: Recommendations for change” report and adopt the Working Forward pledge |  | People and Performance | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2024-12-31
Objective 2: We will take action to ensure we are an equal opportunities employer and reduce pay gaps | Other actions on Employment identified from consultation | 52 | Review Casual Worker Policy to ensure consistency of treatment between workers and that it adequately protects their rights. |  | People and Performance | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2024-12-31
Objective 3: We will take action to improve the Living Standards of people disadvantaged by their protected characteristics | Priority Area 3.1: Take action to address disproportionate negative impact on people with different protected characteristics | 53 | Implement relevant actions from the Disability Rights Action Plan which is currently being developed by Welsh Government's Disability Rights Taskforce | Welsh Government Disability Rights Taskforce | All Services |  | ü | [7 empty] | Review March 2025
Objective 3: We will take action to improve the Living Standards of people disadvantaged by their protected characteristics | Priority Area 3.1: Take action to address disproportionate negative impact on people with different protected characteristics | 54 | Ensure our plans are fully inclusive and targeted to address known health inequalities in access to care and service provision in accordance with our population needs assessment | Anti-racist Wales Action Plan | Social Care | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 3: We will take action to improve the Living Standards of people disadvantaged by their protected characteristics | Priority Area 3.1: Take action to address disproportionate negative impact on people with different protected characteristics | 55 | Review our Equality, Diversity and Inclusion Policy to take into account any legislative changes (e.g. following completion of Welsh Government's review of the Public Sector Equality Duty) |  | People and Performance | ü | ü | ü | ü | ü | ü | ü | ü | ü | Review March 2025
Objective 3: We will take action to improve the Living Standards of people disadvantaged by their protected characteristics | Priority Area 3.1: Take action to address disproportionate negative impact on people with different protected characteristics | 56 | Review our Impact Assessment processes (Equality and Integrated), including exploring digitisation, to ensure that all relevant duties (including the new areas of Health Impact Assessments, the Armed Forces Covenant) and action plans are incorporated and an anti-discriminatory/anti-racist approach is taken | Anti-racist Wales Action Plan / LGBTQ+ Action Plan | People and Performance | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2024-12-31
Objective 3: We will take action to improve the Living Standards of people disadvantaged by their protected characteristics | Priority Area 3.1: Take action to address disproportionate negative impact on people with different protected characteristics | 57 | Establish an older persons' choir at Venue Cymru |  | Economy & Culture | [5 empty] | ü |  |  |  | 2028-03-31
Objective 3: We will take action to improve the Living Standards of people disadvantaged by their protected characteristics | Priority Area 3.1: Take action to address disproportionate negative impact on people with different protected characteristics | 58 | As part of commissioning Housing Support Grant services, ensure that landlords (providers) demonstrate that they are responding quickly to complaints of racism, harassment, discrimination and hate crime and offer appropriate support | Anti-racist Wales Action Plan | Regulatory & Housing (Housing) | ü | [8 empty] | Ongoing
Objective 3: We will take action to improve the Living Standards of people disadvantaged by their protected characteristics | Priority Area 3.1: Take action to address disproportionate negative impact on people with different protected characteristics | 59 | Review existing systems for reporting, and dealing with complaints of discrimination; including the identification and elimination of all forms of discrimination | Anti-racist Wales Action Plan | Audit & Procurement | ü | ü | ü | ü | ü | ü | ü | ü | ü | December 2024 and ongoing
Objective 3: We will take action to improve the Living Standards of people disadvantaged by their protected characteristics | Priority Area 3.1: Take action to address disproportionate negative impact on people with different protected characteristics | 60 | Work with a range of partners towards developing Age Friendly Community status for Conwy |  | Economy & Culture | [5 empty] | ü |  |  |  | 2028-03-31
Objective 3: We will take action to improve the Living Standards of people disadvantaged by their protected characteristics | Priority Area 3.2: Support disabled people, children and older people's right to independent living including adequate accessible and adaptable housing and related support | 61 | Pilot opportunities for people to “pool” their Direct Payments to undertake group activities to address potential isolation |  | Social Care |  | ü |  |  |  | ü |  |  |  | Ongoing
Objective 3: We will take action to improve the Living Standards of people disadvantaged by their protected characteristics | Priority Area 3.2: Support disabled people, children and older people's right to independent living including adequate accessible and adaptable housing and related support | 62 | Explore and deliver extra care housing opportunities in the Colwyn Bay area (e.g. Colwyn Extra Care Housing, Health and Wellbeing Hub Programme) |  | Social Care | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2027-03-31
Objective 3: We will take action to improve the Living Standards of people disadvantaged by their protected characteristics | Priority Area 3.2: Support disabled people, children and older people's right to independent living including adequate accessible and adaptable housing and related support | 63 | Provide accommodation through the Sylva Gardens Project, which will be fit for purpose as children transition to adult life, removing the need for a change in accommodation at 18 and providing consistent care |  | Social Care |  | ü |  |  |  | ü |  |  |  | 2024-09-30
Objective 3: We will take action to improve the Living Standards of people disadvantaged by their protected characteristics | Priority Area 3.2: Support disabled people, children and older people's right to independent living including adequate accessible and adaptable housing and related support | 64 | Disabled people living in the rural area have access to good quality supported living accommodation that meets their needs (Melverley) |  | Social Care – Disability Service | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 3: We will take action to improve the Living Standards of people disadvantaged by their protected characteristics | Priority Area 3.2: Support disabled people, children and older people's right to independent living including adequate accessible and adaptable housing and related support | 65 | Deliver the Sub-Regional Children’s Residential Assessment Centre Project in partnership with Denbighshire and BCUHB where children can stay for up to 12 weeks to be assessed and have care and support plans in place to avoid them becoming children looked after |  | Social Care | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2025-03-31
Objective 3: We will take action to improve the Living Standards of people disadvantaged by their protected characteristics | Priority Area 3.3: Better engagement with disabled people when renovating and designing buildings to ensure full accessibility | 66 | Ensure when Public Convenience are upgraded the work takes into account disability access, gender identity and training / awareness for frontline staff | LGBTQ+ Action Plan | Environment, Roads & Facilities | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2025-03-31
Objective 3: We will take action to improve the Living Standards of people disadvantaged by their protected characteristics | Priority Area 3.3: Better engagement with disabled people when renovating and designing buildings to ensure full accessibility | 67 | Review the Project Management Framework to ensure that appropriate engagement involves disabled people at the initial design phase of projects for new build projects and renovations which will be open to the public |  | People and Performance |  | ü | [7 empty] | 2025-03-31
Objective 3: We will take action to improve the Living Standards of people disadvantaged by their protected characteristics | Priority Area 3.4: Improve access to services for Gypsy and Traveller communities and improve engagement to develop trust | 68 | Provide accommodation for the Gypsy, Roma and Traveller community in line with the Gypsy and Traveller needs assessment (February 2022) in the Deposit Replacement Local Development (RLDP). | Anti-racist Action Plan | Regulatory & Housing | ü | [8 empty] | 2024-12-31
Objective 3: We will take action to improve the Living Standards of people disadvantaged by their protected characteristics | Priority Area 3.4: Improve access to services for Gypsy and Traveller communities and improve engagement to develop trust | 69 | We will undertake a site assessment in line with the Gypsy/Traveller Encampment protocol which may result in us arranging a health assessment, following which we will refer as appropriate. Where Gypsy/Traveller(s) are accessing medical treatment at a local surgery or hospital we may allow the encampment to remain until the treatment has finished. We will report any safeguarding concerns using our usual reporting procedures. | Anti-racist Wales Action Plan | Regulatory & Housing (Housing) | ü | ü |  |  |  | ü |  |  |  | Ongoing
Objective 3: We will take action to improve the Living Standards of people disadvantaged by their protected characteristics | Priority Area 3.4: Improve access to services for Gypsy and Traveller communities and improve engagement to develop trust | 70 | Contribute to a national/regional/local network of transit provision to facilitate travelling life, with consideration for negotiated stopping, as appropriate | Anti-racist Wales Action Plan | Regulatory & Housing (Planning) | ü | [8 empty] | Ongoing
Objective 3: We will take action to improve the Living Standards of people disadvantaged by their protected characteristics | Priority Area 3.5: Ensure that housing, homelessness and asylum services are inclusive of the specific needs of minority groups, including LGBTQ+ people, ethnic minority people and disabled people | 71 | Continue to identify, support and uphold the rights and best interests of unaccompanied asylum-seeking children and young people | Anti-racist Wales Action Plan | Regulatory & Housing (Regulatory) / Social Care | ü |  |  |  |  | ü |  |  |  | Ongoing
Objective 3: We will take action to improve the Living Standards of people disadvantaged by their protected characteristics | Priority Area 3.5: Ensure that housing, homelessness and asylum services are inclusive of the specific needs of minority groups, including LGBTQ+ people, ethnic minority people and disabled people | 72 | Explore training opportunities for Housing staff to ensure that they are fully up to date with the rights and entitlements of EU Citizens and other migrant groups, including those granted refugee status, those seeking asylum, and those with No Recourse to ‘Public Funds. | Anti-racist Wales Action Plan | Regulatory & Housing (Housing) | ü | [8 empty] | Review March 2025
Objective 3: We will take action to improve the Living Standards of people disadvantaged by their protected characteristics | Priority Area 3.5: Ensure that housing, homelessness and asylum services are inclusive of the specific needs of minority groups, including LGBTQ+ people, ethnic minority people and disabled people | 73 | Ensure that the Local Housing Market Assessments (LHMA), and their assessment of needs for ethnic minority people and other key groups inform the prospectus as part of the Social Housing Grant programme monitoring | Anti-racist Wales Action Plan | Regulatory & Housing (Housing) | ü | ü | ü | ü | ü | ü | ü | ü | ü
Objective 3: We will take action to improve the Living Standards of people disadvantaged by their protected characteristics | Priority Area 3.5: Ensure that housing, homelessness and asylum services are inclusive of the specific needs of minority groups, including LGBTQ+ people, ethnic minority people and disabled people | 74 | We will continue to collect equality monitoring data and screen clients seeking housing to ensure that appropriate arrangements are made depending on specific needs relating to protected characteristic, e.g. accessibility, ethnic minority clients, LGBTQ+ accommodation, youth homelessness | Anti-racist Wales Action Plan / LGBTQ+ Action Plan | Regulatory & Housing (Housing) | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 3: We will take action to improve the Living Standards of people disadvantaged by their protected characteristics | Priority Area 3.5: Ensure that housing, homelessness and asylum services are inclusive of the specific needs of minority groups, including LGBTQ+ people, ethnic minority people and disabled people | 75 | Work in partnership to support and advocate on behalf of young person displaying as homeless or likely to become homeless, to end youth homelessness in Conwy by 2027 - including working in partnership with Children's Services to develop housing and support options that avoid the need to place 16 and 17 year olds in Bed and Breakfast |  | Regulatory & Housing (Housing) | [5 empty] | ü |  |  |  | 2027-03-31
Objective 3: We will take action to improve the Living Standards of people disadvantaged by their protected characteristics | Priority Area 3.5: Ensure that housing, homelessness and asylum services are inclusive of the specific needs of minority groups, including LGBTQ+ people, ethnic minority people and disabled people | 76 | Work with ethnic minority-led organisations, Housing Associations, Shelter Cymru and Citizens Advice Cymru to meet the information and advice needs of ethnic minority people in relation to accessing appropriate homes (e.g. Gypsies and Travellers, asylum seekers and refugees) | Anti-racist Wales Action Plan | Regulatory & Housing (Housing) | ü | [5 empty] | ü |  |  | Ongoing
Objective 3: We will take action to improve the Living Standards of people disadvantaged by their protected characteristics | Priority Area 3.5: Ensure that housing, homelessness and asylum services are inclusive of the specific needs of minority groups, including LGBTQ+ people, ethnic minority people and disabled people | 77 | Provide advice and capacity-building support to the Third Sector to ensure those with No Recourse to ‘Public Funds’ (NRPF) are able to access services to which they are entitled to avoid them becoming homeless, more vulnerable to violence and exploitation and treated with compassion and harmful outcomes are avoided. | Anti-racist Wales Action Plan | Regulatory & Housing (Regulatory) | ü | [5 empty] | ü |  |  | Ongoing
Objective 4: We will improve Health, Wellbeing and Social Care outcomes | Priority Area 4.1: Ensure health and wellbeing needs of carers are met | 78 | Continue to support the health and wellbeing needs of carers in line with the regional carers strategy action plan, focussing on four priority areas: identification of carers, provision of information and advice, supporting life alongside caring, and supporting carers in education and the workplace. | North Wales Carers' Strategy | Social Care - Commissioning | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 4: We will improve Health, Wellbeing and Social Care outcomes | Priority Area 4.1: Ensure health and wellbeing needs of carers are met | 79 | Implement a Fostering Friendly Policy for Conwy staff and continue to promote Foster Carer recruitment on a wider basis |  | Social Care | ü | ü | ü | ü | ü | ü | ü | ü | ü | Policy - 31/12/2024 Recruitment - Ongoing
Objective 4: We will improve Health, Wellbeing and Social Care outcomes | Priority Area 4.1: Ensure health and wellbeing needs of carers are met | 80 | Commission services to support the mental well-being of unpaid carers so that they are able to carry out their important role, and can access help in times of crisis and avoid breakdowns in care |  | Social Care | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 4: We will improve Health, Wellbeing and Social Care outcomes | Priority Area 4.1: Ensure health and wellbeing needs of carers are met | 81 | Carers will have access to a range of flexible short breaks |  | Social Care – Disability Service | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2024-12-31
Objective 4: We will improve Health, Wellbeing and Social Care outcomes | Priority Area 4.2: Support the Regional Suicide and Self-harm Prevention Board to implement the relevant Welsh Government strategic plan to reduce suicide and self-harm, especially those with protected characteristics who are at higher risk | 82 | Support the delivery of the regional objectives as set out in the North Wales Suicide and Self-harm Prevention Strategic Plan which includes: Increase awareness and understanding of suicide and self-harm with the priority groups, e.g. LGBTQ+ people, ‘Men in mid-life’ and veterans; to deliver appropriate responses to personal crises; support for those bereaved or affected by suicide and self-harm; reduce access to the means of suicide | LGBTQ+ Action Plan | Social Care – Vulnerable People | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 4: We will improve Health, Wellbeing and Social Care outcomes | Priority Area 4.2: Support the Regional Suicide and Self-harm Prevention Board to implement the relevant Welsh Government strategic plan to reduce suicide and self-harm, especially those with protected characteristics who are at higher risk | 83 | Be a key partner and stakeholder of the Regional Suicide and Self-harm Prevention Board in a coordinated response to a new/updated action plan of the Talk to Me 2 or subsequent policy |  | Social Care – Vulnerable People | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 4: We will improve Health, Wellbeing and Social Care outcomes | Priority Area 4.3: Evaluate progress on mental health to ensure we are meeting the needs of people with different protected characteristics | 84 | Implement an Early Intervention and Prevention approach across Mental Health and Vulnerable People teams |  | Social Care – Mental Health | ü | ü | ü | ü | ü | ü | ü |  |  | 2025-03-31
Objective 4: We will improve Health, Wellbeing and Social Care outcomes | Priority Area 4.3: Evaluate progress on mental health to ensure we are meeting the needs of people with different protected characteristics | 85 | Work with community organisations, the third sector and the NHS to ensure the needs of Black, Asian and Minority Ethnic people are considered when developing: - new strategies and legislation for Mental Health - proposals to address the unmet mental health needs of asylum seekers, refugees and migrants - proposals to reduce health inequalities amongst, Gypsies, Roma and Traveller communities | Anti-racist Wales Action Plan | Social Care | ü | ü |  |  |  |  | ü |  |  | Ongoing
Objective 4: We will improve Health, Wellbeing and Social Care outcomes | Priority Area 4.3: Evaluate progress on mental health to ensure we are meeting the needs of people with different protected characteristics | 86 | Co-produce mental health services in the community in partnership with commissioned stakeholder/focus groups to understand what an inclusive service would look like to ensure fair access for all marginalised groups such as adults with autism, carers and LGBTQ+ groups | LGBTQ+ Action Plan | Social Care – Vulnerable People | ü | ü | ü | ü | ü | ü | ü |  |  | Ongoing
Objective 4: We will improve Health, Wellbeing and Social Care outcomes | Priority Area 4.4: Use Social Model of Disability principles in policy and decision-making | 87 | Work to increase awareness of the importance of embedding the Social Model of Disability into service delivery and employment practices |  | People and Performance |  | ü | [7 empty] | 2025-12-31
Objective 4: We will improve Health, Wellbeing and Social Care outcomes | Priority Area 4.5: Implement specific awareness and support for people with neurological conditions | 88 | Co-ordinate Conwy and Denbighshire's implementation of the actions identified in the local ASC Code of Practice action plan in relation to Local Authority duties, delivering improvement activities for autistic people and their families in Conwy |  | Social Care – Disability Service |  | ü | [7 empty] | 2024-12-31
Objective 4: We will improve Health, Wellbeing and Social Care outcomes | Priority Area 4.5: Implement specific awareness and support for people with neurological conditions | 89 | Develop Neurodiversity in the Workplace Guidance and launch with awareness sessions for managers and staff and involve interested parties in this work |  | People and Performance |  | ü | [7 empty] | 2024-09-30
Objective 4: We will improve Health, Wellbeing and Social Care outcomes | Priority Area 4.5: Implement specific awareness and support for people with neurological conditions | 90 | Engage a Neurodiverse Project Officer to support access to services for neurodivergent people |  | Social Care – Vulnerable People |  | ü | [7 empty] | 2024-12-31
Objective 4: We will improve Health, Wellbeing and Social Care outcomes | Priority Area 4.6: Address barriers to exercise and wellbeing | 91 | Apply for further funding to continue to support the work of “Create” and "Create2". These are arts groups for 12-16 year olds and 20-25 year olds who are experiencing mental health difficulties. Sessions are run every week, to improve mental health and coping through the arts. Participants have to be referred by a mental health practitioner. The group also supports LGBTQ+ issues, particularly coping with family relationship difficulties as a result of LGBTQ+. The value of "Create" work is assessed in partnership with CAMHS using their score charts to work with attendees which shows week on week increases in wellbeing of participants. | LGBTQ+ Action Plan | Economy & Culture | ü | ü | ü | ü | ü | ü | ü |  | ü | Ongoing
Objective 4: We will improve Health, Wellbeing and Social Care outcomes | Priority Area 4.6: Address barriers to exercise and wellbeing | 92 | Provide free spaces for our Children Looked After at our Creative Arts groups which are also attracting young carers, e.g. vertical dance classes |  | Economy & Culture | ü | ü | ü | ü | ü | ü | ü |  | ü | Ongoing
Objective 4: We will improve Health, Wellbeing and Social Care outcomes | Priority Area 4.6: Address barriers to exercise and wellbeing | 93 | Develop new models to promote health & well-being through social prescribing so that people of all ages are less reliant on health and social care (e.g. Creu Conwy Ifanc, Recovery College Model being developed in Colwyn Bay Library). We will do this by working collaboratively and looking at future trends. |  | Economy & Culture | ü | ü | ü | ü | ü | ü | ü |  | ü | Ongoing
Objective 4: We will improve Health, Wellbeing and Social Care outcomes | Priority Area 4.6: Address barriers to exercise and wellbeing | 94 | Work to make our leisure and cultural teams financially sustained and address barriers to exercise and well-being, so that we can retain affordable community provision for all and provide communities with a wide variety of well-being and exercise choices to have More People, More Active, More Often | Corporate Plan 2022-2027 | Economy & Culture | ü | ü | ü | ü | ü | ü | ü |  | ü | 2027-03-31
Objective 4: We will improve Health, Wellbeing and Social Care outcomes | Priority Area 4.6: Address barriers to exercise and wellbeing | 95 | Continue to develop our leisure facilities as community health and wellbeing centres of excellence in partnership with CCBC Social Care and Education Service, BCUHB, Public Health Wales, North Wales Police, Active North Wales and the third sector as per the EIRIAS model |  | Economy & Culture | ü | ü | ü | ü | ü | ü | ü |  | ü | 2027-03-31
Objective 4: We will improve Health, Wellbeing and Social Care outcomes | Priority Area 4.6: Address barriers to exercise and wellbeing | 96 | Ensure that inclusion is a fundamental element of all sport physical activity programmes with a focus on influencing, including and inspiring all who contribute and provide opportunities within Conwy’s sport and leisure sector. Facilitate a progressive approach and utilise the insport programme to enable more disabled people to enjoy lifelong physical activity (including sport). |  | Economy & Culture | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2027-03-31
Objective 4: We will improve Health, Wellbeing and Social Care outcomes | Priority Area 4.6: Address barriers to exercise and wellbeing | 97 | Ensure that programmes continue to offer provision and make positive actions to support the participation in active lifestyles of women and girls from Black, Asian and Minority Ethnic groups, taking account of intersectional disadvantages, languages and the most disadvantaged groups. | Anti-racist Wales Action Plan | Economy & Culture | ü |  | ü | [6 empty] | 2027-03-31
Objective 4: We will improve Health, Wellbeing and Social Care outcomes | Priority Area 4.6: Address barriers to exercise and wellbeing | 98 | Engage and consult with groups/initiatives, and work in collaboration to improve the representation, inclusion, and participation of LGBTQ+ people in sports | LGBTQ+ Action Plan | Economy & Culture |  |  |  | ü | ü |  |  |  |  | 2027-03-31
Objective 4: We will improve Health, Wellbeing and Social Care outcomes | Priority Area 4.6: Address barriers to exercise and wellbeing | 99 | Developing, consulting on and implementing accessible active travel infrastructure to encourage walking, cycling, wheelchair and mobility scooter users, and reduce car use | Corporate Plan 2022-2027 | Environment, Roads & Facilities | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2027-03-01
Objective 4: We will improve Health, Wellbeing and Social Care outcomes | Priority Area 4.7: Increase confidence and support Social Care, and other staff, to highlight and address racist and other discriminatory behaviour experienced while undertaking their roles | 100 | Implement the Health and Social Care Workforce Race Equality Standard referenced in the Anti-racist Wales Action Plan | Anti-racist Wales Action Plan | Social Care | ü | [8 empty] | 2028-03-31
Objective 4: We will improve Health, Wellbeing and Social Care outcomes | Priority Area 4.7: Increase confidence and support Social Care, and other staff, to highlight and address racist and other discriminatory behaviour experienced while undertaking their roles | 101 | Work with partners (e.g. Welsh Government, Social Care Wales) to contribute to the Social Care lived experiences independent review to ensure that people from minority ethnic backgrounds feel safe in the workplace and have full confidence in their leadership to operate a zero-tolerance policy of racism and any other form of discrimination or inequality | Anti-racist Wales Action Plan | Social Care | ü | [8 empty] | 2025-03-31
Objective 4: We will improve Health, Wellbeing and Social Care outcomes | Priority Area 4.7: Increase confidence and support Social Care, and other staff, to highlight and address racist and other discriminatory behaviour experienced while undertaking their roles | 102 | Update the Respect Booklet as a guide for staff delivering key services across the Authority to ensure they consider the rights of different protected groups and the barriers they face, eg, homelessness and housing, supporting asylum seekers, social care, recruitment, etc | Anti-racist Action Plan / LGBTQ+ Action Plan | People and Performance | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2025-03-31
Objective 4: We will improve Health, Wellbeing and Social Care outcomes | Other actions on Health, Wellbeing and Social Care identified from consultation | 103 | Continue to work with disabled people, their carers, the third sector and Public Health Wales on delivering improvements in the priority areas identified in the Welsh Government Learning Disability Strategic Action Plan 2022-2026 |  | Social Care – Disability Service |  | ü |  |  |  | ü |  |  |  | 2026-12-31
Objective 4: We will improve Health, Wellbeing and Social Care outcomes | Other actions on Health, Wellbeing and Social Care identified from consultation | 104 | Review dementia services via Conwy's Dementia Forum to develop services locally, and use information gathered through this work to feed into regional partnership working on dementia services |  | Social Care – Older People |  | ü |  |  |  | ü |  |  |  | 2026-03-31
Objective 4: We will improve Health, Wellbeing and Social Care outcomes | Other actions on Health, Wellbeing and Social Care identified from consultation | 105 | Develop a Conwy-specific action plan to action and deliver the National Action Plan to prevent abuse of older people when it has been published (Engage effectively with the Older People’s Commissioner and other relevant agencies to understand fully the action plan, criteria and expectations) | National Action Plan to Prevent the Abuse of Older People | Social Care | [5 empty] | ü |  |  |  | Review March 2025
Objective 4: We will improve Health, Wellbeing and Social Care outcomes | Other actions on Health, Wellbeing and Social Care identified from consultation | 106 | Utilise Welsh Government's resources such as “Parenting. Give it time” to support the needs of parents and families of LGBTQ+ young people | LGBTQ+ Action Plan | Social Care |  |  |  | ü | ü | ü |  |  |  | Ongoing
Objective 4: We will improve Health, Wellbeing and Social Care outcomes | Other actions on Health, Wellbeing and Social Care identified from consultation | 107 | We will work to support the priorities of the Age Friendly Wales Strategy |  | Social Care | [5 empty] | ü |  |  |  | Review 31/03/2025
Objective 4: We will improve Health, Wellbeing and Social Care outcomes | Other actions on Health, Wellbeing and Social Care identified from consultation | 108 | Work with partners to establish a North Wales Dementia Friendly Communities Scheme (replacing the previous Alzheimer's Society Dementia-Friendly Organisation Scheme) |  | Social Care | [5 empty] | ü |  |  |  | 2026-03-31
Objective 4: We will improve Health, Wellbeing and Social Care outcomes | Other actions on Health, Wellbeing and Social Care identified from consultation | 109 | We will focus on Adverse Childhood Experiences and provide support to parents through multi-agency approaches, particularly around the experiences of disabled people, ethnic minority people, LGBTQ+ people and other minority groups | Anti-racist Wales Action Plan / LGBTQ+ Action Plan | Social Care | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 5: We will improve Personal Security and Access to Justice | Priority Area 5.1: Work with our North Wales partners to increase awareness of Hate Crime and increase confidence in reporting | 110 | We will continue to tackle Modern Slavery and Human Trafficking with our North Wales partners and regularly review progress to determine our priority areas for action |  | Regulatory & Housing (Community Safety) | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 5: We will improve Personal Security and Access to Justice | Priority Area 5.1: Work with our North Wales partners to increase awareness of Hate Crime and increase confidence in reporting | 111 | Continue to raise awareness of the impact of hate crime on victims from ethnic minority communities, LGBTQ+ communities and other protected groups through the ‘Hate Hurts Wales’ campaign. This campaign will address victims, perpetrators and bystanders through various materials. Campaign materials will be developed with those who have been affected by racist or other hate crime. | Anti-racist Wales Action Plan / LGBTQ+ Action Plan | Regulatory & Housing (Community Safety) | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 5: We will improve Personal Security and Access to Justice | Priority Area 5.1: Work with our North Wales partners to increase awareness of Hate Crime and increase confidence in reporting | 112 | Continue to work with the North Wales Public Sector Equality Network to raise awareness about Hate Crime, particularly during Hate Crime Awareness week with our North Wales partners, including awareness raising around anti-racism and tackling anti-semitism and islamaphobia | Anti-racist Wales Action Plan | People and Performance | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 5: We will improve Personal Security and Access to Justice | Priority Area 5.1: Work with our North Wales partners to increase awareness of Hate Crime and increase confidence in reporting | 113 | Maintain links with the North Wales Community Cohesion team to support initiatives to improve community cohesion | Anti-racist Wales Action Plan | Regulatory & Housing (Community Safety) / People and Performance (Equalities) | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 5: We will improve Personal Security and Access to Justice | Priority Area 5.2: Work with North Wales partners to reduce incidents of Violence Against Women, Domestic Abuse and Sexual Violence (VAWDASV) | 114 | Support the regional Independent Domestic Violence Advice Service based with the North Wales Women's Centre in Rhyl and by the Domestic Abuse Safety Unit for both Denbighshire and Conwy |  | Regulatory & Housing (Community Safety) | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 5: We will improve Personal Security and Access to Justice | Priority Area 5.2: Work with North Wales partners to reduce incidents of Violence Against Women, Domestic Abuse and Sexual Violence (VAWDASV) | 115 | Implement the training commitments made in our Violence against Women, Domestic Abuse and Sexual Violence Policy, specifically the delivery and monitoring of Group 1 and Group 2 training of the workforce, as well as the Group 3 training commitment to develop champions in each of our Service areas |  | People and Performance |  |  | ü | [6 empty] | 2025-03-31
Objective 5: We will improve Personal Security and Access to Justice | Priority Area 5.2: Work with North Wales partners to reduce incidents of Violence Against Women, Domestic Abuse and Sexual Violence (VAWDASV) | 116 | Support the actions on the Violence Against Women, Domestic Abuse and Sexual Violence Strategy ensuring that appropriate prevention programmes are delivered and implemented; survivors receive appropriate and timely support (including specialist support for children and young people, disabled people, ethnic minority people, LGBTQ+ people and people with complex needs) | Anti-racist Wales Action Plan / LGBTQ+ Action Plan | Regulatory & Housing / Social Care | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 5: We will improve Personal Security and Access to Justice | Priority Area 5.3: Improve awareness of personal safety and safeguarding responsibilities | 117 | Specifically target the voice of older people and hard to reach groups, considering promotion on social media and highlighting safeguarding with a variety of communities |  | Social Care | [5 empty] | ü |  |  |  | 2024-12-31
Objective 5: We will improve Personal Security and Access to Justice | Priority Area 5.3: Improve awareness of personal safety and safeguarding responsibilities | 118 | The Disability Service Sexuality & Relationship Policy, including Easy Read version, supports the rights of people with disabilities to have personal relationships and healthy sex lives |  | Social Care – Disability Service |  | ü |  | ü | ü |  |  | ü |  | 2024-12-31
Objective 5: We will improve Personal Security and Access to Justice | Priority Area 5.3: Improve awareness of personal safety and safeguarding responsibilities | 119 | Safer Conwy to work with our third sector partners to support awareness raising and support the live fear free all Wales helpline. |  | Regulatory & Housing (Community Safety) | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 6: Increase Access to Participation and improve diversity in decision making | Priority Area 6.1: Increase awareness of the importance of diversity in political representation and decision making bodies | 120 | Develop (and deliver on) an action plan to support the Diverse Council Declaration, to increase the diversity of candidates in local government elections (e.g. disabled people, ethnic minority people, LGBTQ+ people) | Corporate Plan 2022-2027 / Anti-racist Wales Action Plan / LGBTQ+ Action Plan | Law and Governance | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2027-05-31
Objective 6: Increase Access to Participation and improve diversity in decision making | Priority Area 6.1: Increase awareness of the importance of diversity in political representation and decision making bodies | 121 | Finalise approval of the Public Participation Strategy and deliver on the actions within the Strategy to promote access to Local Government, in line with the Duty to encourage people to participate in Local Government decision making |  | Law and Governance | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 6: Increase Access to Participation and improve diversity in decision making | Priority Area 6.1: Increase awareness of the importance of diversity in political representation and decision making bodies | 122 | Promote the expanded (Welsh Government) Access to Elected Office fund for the next local government elections in 2027 | Anti-racist Wales Action Plan / LGBTQ+ Action Plan | Law and Governance | ü | ü |  | ü | ü |  | ü |  |  | 2027-05-31
Objective 6: Increase Access to Participation and improve diversity in decision making | Priority Area 6.1: Increase awareness of the importance of diversity in political representation and decision making bodies | 123 | As they are available, promote access to schemes for diverse role models for participation in democracy, including standing for office, and schemes such as the "Equal Power, Equal Voices" Public Life Mentoring Programme | Anti-racist Action Plan / LGBTQ+ Action Plan | Law and Governance | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 6: Increase Access to Participation and improve diversity in decision making | Priority Area 6.1: Increase awareness of the importance of diversity in political representation and decision making bodies | 124 | Implement digital solutions to support streaming and participation in our democratic meetings to increase accessibility |  | Law and Governance / Information Technology | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2027-03-31
Objective 6: Increase Access to Participation and improve diversity in decision making | Priority Area 6.1: Increase awareness of the importance of diversity in political representation and decision making bodies | 125 | We will ensure organisations we support financially, subject to funding, (e.g. via Shared Prosperity Funding) capture / review baseline equality monitoring data (including ethnicity data) across the organisation and, as appropriate, implement steps to increase diversity at all levels, specifically in leadership teams and on boards, by following fair 'positive' recruitment processes and providing quality job opportunities and measure progress | Anti-racist Wales Action Plan | Economy & Culture | [9 empty] | Ongoing
Objective 6: Increase Access to Participation and improve diversity in decision making | Priority Area 6.2: Ensure engagement is inclusive to provide a sense of belonging and community | 126 | Conwy, in partnership with North Wales Local Authorities and BCUHB, have commissioned a support service for the 'North Wales Flyer' participation group. The group reports into the North Wales Learning Disability Partnership and advises partners of priorities identified by disabled people. The group are supported by All-Wales People First, Conwy Connect and the NWAAA Consortium. The Chair is the Vice Chair of the North Wales Regional Transformation Programme Board |  | Social Care - Disability Service | [9 empty] | Ongoing
Objective 6: Increase Access to Participation and improve diversity in decision making | Priority Area 6.2: Ensure engagement is inclusive to provide a sense of belonging and community | 127 | Review and promote training on engagement and consultation ensuring that our engagement on designing our services, policies and practices is inclusive and involves people with different protected characteristics, particularly LGBTQ+ people, ethnic minorities, older people in care homes as well as children and young people who can often be overlooked | Anti-racist Wales Action Plan / LGBTQ+ Action Plan | People and Performance / All Services | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 6: Increase Access to Participation and improve diversity in decision making | Priority Area 6.2: Ensure engagement is inclusive to provide a sense of belonging and community | 128 | Review our Equality Impact Assessment Policy when digitisation has been explored |  | People and Performance | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2026-03-31
Objective 6: Increase Access to Participation and improve diversity in decision making | Priority Area 6.2: Ensure engagement is inclusive to provide a sense of belonging and community | 129 | Review the Conwy Communications Strategy user guide to ensure marketing and advertising materials and social media content are anti-racist and reflect the true depth of our diverse cultural heritage while avoiding stereotyping and cultural appropriation by seeking out and working with Black, Asian and Minority Ethnic groups and individuals, to uncover untold stories and celebrate success. | Anti-racist Wales Action Plan | Economy & Culture (Marketing) | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2025-03-31
Objective 6: Increase Access to Participation and improve diversity in decision making | Priority Area 6.2: Ensure engagement is inclusive to provide a sense of belonging and community | 130 | To consider the feasibility and interest in establishing staff group(s) for different protected groups with lived experience to engage and involve staff in the development of policy and practices to ensure anti-discriminatory practice and not just non-discriminatory practice and to support wellbeing. | Anti-racist Action Plan | People and Performance | ü | ü | ü | ü | ü | ü | ü |  | ü | 2025-03-31
Objective 6: Increase Access to Participation and improve diversity in decision making | Priority Area 6.2: Ensure engagement is inclusive to provide a sense of belonging and community | 131 | Co-design opportunities with grassroots community-based organisations to engage Black Asian and Minority Ethnic individuals (including women, girls, disabled people, elders, LGBTQ+ people, and people whose first language is not English or Welsh) to express their creativity, heritage, language, cultural identity and origins. These activities will allow people to come together to celebrate our diverse but shared cultural heritage including through visual and performing arts, including contemporary street art, fashion, poetry, dance, sport and music. | Anti-racist Wales Action Plan | Economy & Culture | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 6: Increase Access to Participation and improve diversity in decision making | Priority Area 6.2: Ensure engagement is inclusive to provide a sense of belonging and community | 132 | Review and decolonise our public spaces and collections by appropriately addressing the way in which people and events with known historical associations to slavery and colonialism are commemorated, acknowledging the harm done by their actions and reframing the presentation of their legacy to fully recognise this. | Anti-racist Wales Action Plan | Economy & Culture | ü | [5 empty] | ü |  |  | 2025-03-31
Objective 6: Increase Access to Participation and improve diversity in decision making | Priority Area 6.2: Ensure engagement is inclusive to provide a sense of belonging and community | 133 | Work with Black, Asian and Minority Ethnic communities to identify and lift barriers to accessing heritage sites and cultural collections. Tell stories through the lens of Black, Asian and Minority Ethnic people’s experiences (past and present) in our galleries, libraries and museums, including through permanent displays, celebrating their contribution and recognising their presence in the history of Wales. | Anti-racist Wales Action Plan | Economy & Culture | ü | [5 empty] | ü |  |  | Ongoing
Objective 6: Increase Access to Participation and improve diversity in decision making | Priority Area 6.2: Ensure engagement is inclusive to provide a sense of belonging and community | 134 | Increase the involvement of LGBTQ+ people and organisations in the design of cultural events and activities (e.g. Museum Service work to identify and develop queer narratives for North Wales) | LGBTQ+ Action Plan | Economy & Culture |  |  | ü | ü | ü |  |  |  |  | Ongoing
Objective 6: Increase Access to Participation and improve diversity in decision making | Priority Area 6.2: Ensure engagement is inclusive to provide a sense of belonging and community | 135 | Use LGBTQ+ awareness events to amplify LGBTQ+ voices (e.g. LGBTQ+ History Month, support for events to mark important dates) | LGBTQ+ Action Plan | All Services |  |  | ü | ü | ü |  |  |  |  | Ongoing
Objective 6: Increase Access to Participation and improve diversity in decision making | Priority Area 6.2: Ensure engagement is inclusive to provide a sense of belonging and community | 136 | Create and roll out guidance on how to counter online discriminatory hateful attitudes, including guidance on ensuring that language on the Council's website is anti-discriminatory rather than just non-discriminatory | Anti-racist Wales Action Plan | People and Performance | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2025-03-31
Objective 6: Increase Access to Participation and improve diversity in decision making | Priority Area 6.2: Ensure engagement is inclusive to provide a sense of belonging and community | 137 | Review relevant sections of the Council's website to ensure the language used is anti-discriminatory rather than just non-discriminatory. | Anti-racist Action Plan | All Services | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2025-03-31
Objective 6: Increase Access to Participation and improve diversity in decision making | Priority Area 6.2: Ensure engagement is inclusive to provide a sense of belonging and community | 138 | Work with funding bodies to co-produce bids from small or Black, Asian and Minority Ethnic-led organisations to improve outcomes for Black, Asian and Minority Ethnic groups | Anti-racist Wales Action Plan | Economy & Culture | ü | [5 empty] | ü |  |  | Ongoing
Objective 6: Increase Access to Participation and improve diversity in decision making | Priority Area 6.2: Ensure engagement is inclusive to provide a sense of belonging and community | 139 | Work with relevant partners and groups to review heritage collections and ensure minority groups are represented in our historical collections | Anti-racist Wales Action Plan | Economy & Culture | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 6: Increase Access to Participation and improve diversity in decision making | Priority Area 6.2: Ensure engagement is inclusive to provide a sense of belonging and community | 140 | Maximise the use of volunteers across libraries, culture and the wider sector through the Amdani! partnership project, utilising the Amdani! resources developed in partnership with Disability Arts Cymru and CVSC to open up access to volunteering in the cultural sector |  | Economy & Culture | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2025-03-31
Objective 6: Increase Access to Participation and improve diversity in decision making | Priority Area 6.3: Access to services should be supported by appropriate language support, including Welsh, British Sign Language and other languages | 141 | Continue to promote Welsh language learning opportunities and Welsh language promotion to support Cymraeg 2050, the million Welsh speakers Welsh Government target | Corporate Plan 2022-2027 | Law and Governance / All Services | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 6: Increase Access to Participation and improve diversity in decision making | Priority Area 6.3: Access to services should be supported by appropriate language support, including Welsh, British Sign Language and other languages | 142 | Await and then act on Welsh Government's planned work to gain a better understanding of the lived experience of Welsh speakers from ethnic minority communities to inform future actions and interventions that we can undertake in Conwy | Anti-racist Wales Action Plan | Law and Governance | ü | [8 empty] | Review March 2025
Objective 6: Increase Access to Participation and improve diversity in decision making | Priority Area 6.3: Access to services should be supported by appropriate language support, including Welsh, British Sign Language and other languages | 143 | Ensure that standard wording is included on key policies and strategies regarding how to receive information in alternative formats (and where services can access them) |  | People and Performance / Economy & Culture (Marketing) | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2025-03-31
Objective 6: Increase Access to Participation and improve diversity in decision making | Priority Area 6.3: Access to services should be supported by appropriate language support, including Welsh, British Sign Language and other languages | 144 | To provide support and monitor provision and outcomes for English/Welsh as an Additional Language (EAL) learners |  | Education | ü | [8 empty] | 2024-12-31
Objective 6: Increase Access to Participation and improve diversity in decision making | Priority Area 6.3: Access to services should be supported by appropriate language support, including Welsh, British Sign Language and other languages | 145 | Increase the number of Welsh Language events in Venue Cymru and Theatr Colwyn |  | Economy & Culture | ü | [8 empty] | Ongoing
Objective 6: Increase Access to Participation and improve diversity in decision making | Priority Area 6.3: Access to services should be supported by appropriate language support, including Welsh, British Sign Language and other languages | 146 | Continue to make our communications accessible. We will use plain English and Cymraeg Clir (plain Welsh) and provide translation / interpretation support to ensure people understand what their Council is doing and how they can contribute | Corporate Plan 2022-2027 | Economy & Culture (Marketing) | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2027-03-31
Objective 6: Increase Access to Participation and improve diversity in decision making | Priority Area 6.4: Improve access to services by ensuring an offer of alternative means to technology to prevent digital exclusion | 147 | Continue to support the national and local digital inclusion agendas, e.g. commissioning work to look at the exploitation of Digital Technology Opportunities for the rural area of Conwy and seek funding from Welsh Government for Wi-Fi infrastructure |  | Economy & Culture | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 6: Increase Access to Participation and improve diversity in decision making | Priority Area 6.4: Improve access to services by ensuring an offer of alternative means to technology to prevent digital exclusion | 148 | Implement a revised Customer Service Strategy which strengthens our approach to digital inclusion |  | Economy & Culture |  | ü |  |  |  | ü
Objective 6: Increase Access to Participation and improve diversity in decision making | Priority Area 6.4: Improve access to services by ensuring an offer of alternative means to technology to prevent digital exclusion | 149 | Implement the Digital Strategy to ensure Council digital services offer a range of channels and are accessible |  | Information Technology / All Services |  | ü |  |  |  | ü |  |  |  | 2027-03-31
Objective 6: Increase Access to Participation and improve diversity in decision making | Other actions on Participation and diversity in decision making identified from consultation | 150 | To deliver Creu Conwy, the Culture Strategy, to embed culture in strategy and planning; Guide, inform and inspire planning and investment over the 10 year period; Support and guide existing place-making, regeneration plans and strategies; Increase recognition of the financial and social value of the county’s cultural sector; and develop the potential of cultural participation to contribute to health and wellbeing through strengthened links with social care and health partners and maximising the potential of social prescribing. |  | Economy & Culture | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2028-03-31
Objective 6: Increase Access to Participation and improve diversity in decision making | Other actions on Participation and diversity in decision making identified from consultation | 151 | Celebrate and improve the representation of LGBTQ+ communities in the heritage and culture of Conwy, through partnership working | LGBTQ+ Action Plan | Economy & Culture |  |  | ü | ü | ü |  |  |  |  | Ongoing
Objective 6: Increase Access to Participation and improve diversity in decision making | Other actions on Participation and diversity in decision making identified from consultation | 152 | Encourage employers to promote, share and adopt best practice in relation to inclusive workplaces through our Business Services Communications Channel, e.g. information, advice, guidance and support for employers on employing LGBTQ+ workers | LGBTQ+ Action Plan | Economy & Culture | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 6: Increase Access to Participation and improve diversity in decision making | Other actions on Participation and diversity in decision making identified from consultation | 153 | Continue to work with Chartered Institute of Library & Information Professionals (CILIP) and other partners to develop anti-racist library collections as part of the reader-centred library to represent underrepresented groups in our collections | Anti-racist Wales Action Plan | Economy & Culture | ü | [5 empty] | ü |  |  | Ongoing
Objective 6: Increase Access to Participation and improve diversity in decision making | Other actions on Participation and diversity in decision making identified from consultation | 154 | Provide recognition of non-binary and intersex people in our policies, practices and data collection systems | LGBTQ+ Action Plan | All Services |  |  | ü | ü | [5 empty] | Ongoing
Objective 7: Tackle socio-economic disadvantage by offering inclusive services to minimise inequalities of outcome | Priority Area 7.1: Increase awareness of the links between poverty and ill health with different protected characteristics | 155 | Ensuring that all public facing services identify a champion for poverty and social inclusion, through an Anti-Poverty Steering Group |  | Social Care | ü | ü | ü | ü | ü | ü | ü | ü | ü
Objective 7: Tackle socio-economic disadvantage by offering inclusive services to minimise inequalities of outcome | Priority Area 7.1: Increase awareness of the links between poverty and ill health with different protected characteristics | 156 | Develop training for staff and members about poverty and social inclusion |  | Social Care | ü | ü | ü | ü | ü | ü | ü | ü | ü
Objective 7: Tackle socio-economic disadvantage by offering inclusive services to minimise inequalities of outcome | Priority Area 7.1: Increase awareness of the links between poverty and ill health with different protected characteristics | 157 | Working together through our universal and community-based services to alleviate poverty and support people in poverty |  | Social Care – Community Wellbeing | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 7: Tackle socio-economic disadvantage by offering inclusive services to minimise inequalities of outcome | Priority Area 7.1: Increase awareness of the links between poverty and ill health with different protected characteristics | 158 | Initiate an Equality bulletin looking at socio-economic disadvantage |  | People and Performance | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2025-03-31
Objective 7: Tackle socio-economic disadvantage by offering inclusive services to minimise inequalities of outcome | Priority Area 7.2: Address anti-social behaviour | 159 | Work in partnership to reduce crime and disorder in Conwy and Denbighshire by reducing incidents of victim based crime and Anti-Social Behaviour (ASB) for victims and perpetrators |  | Regulatory & Housing (Community Safety) | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 7: Tackle socio-economic disadvantage by offering inclusive services to minimise inequalities of outcome | Priority Area 7.2: Address anti-social behaviour | 160 | Working towards making all of our public buildings ‘Safe Places’ (a Safe Place offers help if someone is anxious, scared or at risk while they are out and about and need support) | Corporate Plan 2022-2027 | All Services | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2027-03-31
Objective 7: Tackle socio-economic disadvantage by offering inclusive services to minimise inequalities of outcome | Priority Area 7.3: Remove barriers experienced by people due to socio-economic disadvantage | 161 | Deliver the Economic Growth Strategy, including; improving the night time economy and winter tourism; tidal lagoon and renewable energy; state of the art business premises to encourage major economic development; lrotection of employment land to improve the local economy |  | Economy & Culture | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2027-12-31
Objective 7: Tackle socio-economic disadvantage by offering inclusive services to minimise inequalities of outcome | Priority Area 7.3: Remove barriers experienced by people due to socio-economic disadvantage | 162 | Identify recovery and regeneration strategies, linked to the Place Plans for Conwy's 8 major towns: Abergele and Pensarn; Towyn and Kinmel Bay; Colwyn Bay (to include Mochdre, Rhos on Sea and Old Colwyn); Conwy (to include Deganwy and Llandudno Junction); Llanrwst; Llandudno (to include Craig y Don, Penrhyn Bay and Llandrillo yn Rhos), Llanfairfechan; Penmaenmawr |  | Economy & Culture | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2024-12-31
Objective 7: Tackle socio-economic disadvantage by offering inclusive services to minimise inequalities of outcome | Priority Area 7.3: Remove barriers experienced by people due to socio-economic disadvantage | 163 | Develop and deliver an action plan to deliver the Destination Conwy Management Plan 2023-2029, making Conwy a sustainable and buoyant tourist destination |  | Economy & Culture | ü | ü | ü | ü | ü | ü | ü | ü | ü | Review 31/03/2028
Objective 7: Tackle socio-economic disadvantage by offering inclusive services to minimise inequalities of outcome | Priority Area 7.3: Remove barriers experienced by people due to socio-economic disadvantage | 164 | Launch an 'Access Membership' for Ffit Conwy to support low income households to access Leisure facilities |  | Economy & Culture | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2024-12-31
Objective 7: Tackle socio-economic disadvantage by offering inclusive services to minimise inequalities of outcome | Priority Area 7.4: Increase support for children and young people living in poverty to improve outcomes | 165 | Roll out and monitor the Welsh Government initiative of universal primary free school meals |  | Education | ü | ü | ü | ü | ü | ü | ü |  |  | 2025-03-31
Objective 7: Tackle socio-economic disadvantage by offering inclusive services to minimise inequalities of outcome | Priority Area 7.4: Increase support for children and young people living in poverty to improve outcomes | 166 | To co-ordinate the Period Dignity Grant for schools and communities |  | Education | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2025-03-31

## Actions Ongoing
Objective | Priority Area | # | Action | Source / Related Plan(s) | Responsibility | Race | Disability | Sex | Gender Reassignment | Sexual Orientation | Age | Religion/Belief | Marriage/ Civil Partnership | Pregnancy/ Maternity | Complete by
Objective 1: Outcomes in education learning and wellbeing are improved | Priority Area 1.1: All children and young people attend schools regularly and achieve their learning potential | 167 | We will continue to develop the role of Conwy’s Youth Council to ensure the voices of young people are heard by meeting on a monthly basis to discuss relevant topics that affect them |  | Education | ü | ü | ü | ü | ü | ü | ü |  | ü | Ongoing
Objective 1: Outcomes in education learning and wellbeing are improved | Priority Area 1.3: Children and young people are safe and feel safe at school, have equal opportunities, and are encouraged to live a healthy lifestyle | 168 | To promote and signpost parents and people of all ages to relevant resources which will enable them to stay safe online |  | Social Care / Education | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 1: Outcomes in education learning and wellbeing are improved | Priority Area 1.3: Children and young people are safe and feel safe at school, have equal opportunities, and are encouraged to live a healthy lifestyle | 169 | Continue to run take pART which now incorporates arts and science with involvement of more organisations to extend the experience (subject to funding) to give young people opportunities to experience a broad range of STEAM activities outside of the school environment |  | Economy & Culture | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 1: Outcomes in education learning and wellbeing are improved | Priority Area 1.3: Children and young people are safe and feel safe at school, have equal opportunities, and are encouraged to live a healthy lifestyle | 170 | Introduce annual checks to remind parents about claiming Free School Meals / School Essential Grants, with assistance from the Education Department, to ensure take up for those eligible |  | Revenues & Benefits | ü | ü | ü | ü | ü | ü | ü | ü | ü | Annually
Objective 1: Outcomes in education learning and wellbeing are improved | Priority Area 1.5: To support everyone under the age of 25 to access an offer of work, education, training, or self-employment | 171 | Report progress on figures for pupils who are Not in Education, Employment, or Training (NEET) by academic year |  | Education | ü | ü | ü | ü | ü | ü | ü | ü | ü | Annually
Objective 1: Outcomes in education learning and wellbeing are improved | Priority Area 1.5: To support everyone under the age of 25 to access an offer of work, education, training, or self-employment | 172 | Led by Grwp Llandrillo Menai, deliver the ADTRAC project to support those identified as NEET (Not in Education Employment or Training) aged 16-24 to overcome barriers and engage in skills and employment opportunities |  | Education | ü | ü | ü | ü | ü | ü | ü | ü | ü
Objective 1: Outcomes in education learning and wellbeing are improved | Priority Area 1.5: To support everyone under the age of 25 to access an offer of work, education, training, or self-employment | 173 | Continue to deliver Communities for Work (C4W) Welsh Government projects targeting those aged 25+ economically inactive or long term unemployed and NEETS aged 16-24, to overcome barriers to skills and employment. |  | Education | ü | ü | ü | ü | ü | ü | ü | ü | ü
Objective 2: We will take action to ensure we are an equal opportunities employer and reduce pay gaps | Priority Area 2.2: Review our (flexible) working practices to ensure equal opportunities at all levels | 174 | Raise awareness of the facilities and activities available to parents in Conwy County that Council staff can access, including for non-office based staff |  | Social Care – Community Wellbeing | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 2: We will take action to ensure we are an equal opportunities employer and reduce pay gaps | Priority Area 2.4: Increase the number of disabled people in work | 175 | Continue to promote and initiate Time to Change activitives through the champions group to challenge stigma and discrimination faced by people with mental health problems and to improve attitudes and change behaviour towards mental health in society. |  | People and Performance | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 2: We will take action to ensure we are an equal opportunities employer and reduce pay gaps | Priority Area 2.7: Consider the use of positive action measures in recruitment campaigns where specific groups are under-represented | 176 | We will continue to improve our position on equality data collection from staff, encouraging disclosure so that we can make better use of positive action measures |  | People and Performance | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 3: We will take action to improve the Living Standards of people disadvantaged by their protected characteristics | Priority Area 3.1: Take action to address disproportionate negative impact on people with different protected characteristics | 177 | Ensure Equality Impact Assessments are undertaken on policies and practices and action is taken to address where negative impact is identified |  | All Services | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 3: We will take action to improve the Living Standards of people disadvantaged by their protected characteristics | Priority Area 3.1: Take action to address disproportionate negative impact on people with different protected characteristics | 178 | Ensure dedicated resources are in place targeted at tackling homelessness amongst prison leavers |  | Regulatory & Housing (Housing) | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 3: We will take action to improve the Living Standards of people disadvantaged by their protected characteristics | Priority Area 3.1: Take action to address disproportionate negative impact on people with different protected characteristics | 179 | Welfare Reform Project – continue to raise awareness of Universal Credit and ensure the protection of specific groups (eg, mixed age couples, single parents, disability) to maximise the benefit claims they are entitled to |  | Revenues & Benefits | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 3: We will take action to improve the Living Standards of people disadvantaged by their protected characteristics | Priority Area 3.1: Take action to address disproportionate negative impact on people with different protected characteristics | 180 | Continue to be a member of “Hynt” Wales scheme – for disabled people to use their Hynt card around Wales (offers attendance of a companion for free,) and access needs are registered on box office systems to avoid repeating any special facility requirements every time they make a booking. |  | Economy & Culture |  | ü |  |  |  | ü |  |  |  | Ongoing
Objective 3: We will take action to improve the Living Standards of people disadvantaged by their protected characteristics | Priority Area 3.1: Take action to address disproportionate negative impact on people with different protected characteristics | 181 | Continue to provide relaxed performances, subtitled film showings in Theatr Colwyn, Audio described films, signed and audio described performances in Venue Cymru when there are week-long shows running as funding allows |  | Economy & Culture |  | ü |  |  |  | ü |  |  |  | Ongoing
Objective 3: We will take action to improve the Living Standards of people disadvantaged by their protected characteristics | Priority Area 3.1: Take action to address disproportionate negative impact on people with different protected characteristics | 182 | Work in partnership to develop an integrated and holistic approach to tackling the underlying causes of homelessness, through joined up service delivery, joint protocols and effective referral arrangements. |  | Regulatory & Housing (Housing) | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 3: We will take action to improve the Living Standards of people disadvantaged by their protected characteristics | Priority Area 3.1: Take action to address disproportionate negative impact on people with different protected characteristics | 183 | Undertake an awareness raising campaign in relation to homeless prevention, and specifically Conwy Housing Solutions |  | Regulatory & Housing (Housing) | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 3: We will take action to improve the Living Standards of people disadvantaged by their protected characteristics | Priority Area 3.1: Take action to address disproportionate negative impact on people with different protected characteristics | 184 | Equality Champions will continue to support their services in mainstreaming equalities and ensuring compliance with the Public Sector Equality Duty, supporting the work of other equality action plans, and encouraging other interested parties to participate |  | Equality Champions | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 3: We will take action to improve the Living Standards of people disadvantaged by their protected characteristics | Priority Area 3.1: Take action to address disproportionate negative impact on people with different protected characteristics | 185 | Continue to include equalities and the 7 Equality Objectives in audit programmes to test this is being embedded and actions are undertaken |  | Audit & Procurement | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 3: We will take action to improve the Living Standards of people disadvantaged by their protected characteristics | Priority Area 3.1: Take action to address disproportionate negative impact on people with different protected characteristics | 186 | Support activities to acknowledge Holocaust Memorial Day | Anti-racist Wales Action Plan | People and Performance | ü | [5 empty] | ü |  |  | Annually
Objective 3: We will take action to improve the Living Standards of people disadvantaged by their protected characteristics | Priority Area 3.1: Take action to address disproportionate negative impact on people with different protected characteristics | 187 | We will consider how we will continue to deliver services for schools and community transport in the longer term with the changes to legislation affecting accessibility regulations of buses |  | ERF / Education / Social Care | ü | ü | ü | ü | ü | ü | ü | ü | ü
Objective 3: We will take action to improve the Living Standards of people disadvantaged by their protected characteristics | Priority Area 3.1: Take action to address disproportionate negative impact on people with different protected characteristics | 188 | We will ensure all contracts with Conwy Council when renegotiated for non-commercial bus routes (this covers less than 10% of all routes) will have a requirement within the grant to encourage providers to train staff around disability access |  | Environment, Roads & Facilities | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 3: We will take action to improve the Living Standards of people disadvantaged by their protected characteristics | Priority Area 3.2: Support disabled people, children and older people's right to independent living including adequate accessible and adaptable housing and related support | 189 | Continue to work to increase the profile of Direct Payments (both internally with frontline staff and externally with Conwy residents), via a new training programme for staff and promotion to ensure that people are aware of the Direct Payments scheme |  | Social Care | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 3: We will take action to improve the Living Standards of people disadvantaged by their protected characteristics | Priority Area 3.2: Support disabled people, children and older people's right to independent living including adequate accessible and adaptable housing and related support | 190 | To construct adapted affordable housing to meet the needs of disabled people and minority groups in line with the Council’s Local Housing Market Assessment |  | Regulatory & Housing (Planning) | ü | ü |  | ü | ü | ü | ü |  |  | Ongoing
Objective 3: We will take action to improve the Living Standards of people disadvantaged by their protected characteristics | Priority Area 3.2: Support disabled people, children and older people's right to independent living including adequate accessible and adaptable housing and related support | 191 | Monitor the demand and service delivery of the Disabled Facilities Grant (DFG), and implement service improvements where necessary |  | Regulatory & Housing (Housing) |  | ü |  |  |  | ü |  |  |  | Ongoing
Objective 3: We will take action to improve the Living Standards of people disadvantaged by their protected characteristics | Priority Area 3.2: Support disabled people, children and older people's right to independent living including adequate accessible and adaptable housing and related support | 192 | Provide housing related support for vulnerable residents in Conwy, with the end goal being independent living |  | Regulatory & Housing (Housing) | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 3: We will take action to improve the Living Standards of people disadvantaged by their protected characteristics | Priority Area 3.2: Support disabled people, children and older people's right to independent living including adequate accessible and adaptable housing and related support | 193 | Monitor the housing needs of local people to ensure their housing needs are fully understood and a range of housing options are available |  | Regulatory & Housing (Housing) | ü | ü |  | ü | ü | ü |  | ü |  | Ongoing
Objective 3: We will take action to improve the Living Standards of people disadvantaged by their protected characteristics | Priority Area 3.2: Support disabled people, children and older people's right to independent living including adequate accessible and adaptable housing and related support | 194 | Maintain an efficient service in respect of enforcement of Planning and Building Control to keep communities safe |  | Regulatory & Housing (Development and Building Control) | ü | ü | ü | ü | ü | ü | ü |  | ü | Ongoing
Objective 3: We will take action to improve the Living Standards of people disadvantaged by their protected characteristics | Priority Area 3.2: Support disabled people, children and older people's right to independent living including adequate accessible and adaptable housing and related support | 195 | Increase the supply of appropriate affordable and market housing which meets identified need, including site development design to ensure accessibility for all protected groups |  | Regulatory & Housing (Planning) | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 3: We will take action to improve the Living Standards of people disadvantaged by their protected characteristics | Priority Area 3.2: Support disabled people, children and older people's right to independent living including adequate accessible and adaptable housing and related support | 196 | Continue to implement Part M of the Building Regulations to all developments that apply to Conwy for Building Regulations which requires housebuilders to construct new housing to standards that enable disabled people, particularly wheelchair users and those with mobility or ambulant impairments, to visit a house and have access to a ground floor living space and toilet |  | Regulatory & Housing (Development and Building Control) |  | ü |  |  |  | ü |  |  |  | Ongoing
Objective 3: We will take action to improve the Living Standards of people disadvantaged by their protected characteristics | Priority Area 3.2: Support disabled people, children and older people's right to independent living including adequate accessible and adaptable housing and related support | 197 | Continue to work with partners to support older people who need support to stay independent within their own homes via Community Resource Teams |  | Social Care – Older People | ü | ü | ü | ü | ü | ü | ü | ü |  | Ongoing
Objective 3: We will take action to improve the Living Standards of people disadvantaged by their protected characteristics | Priority Area 3.2: Support disabled people, children and older people's right to independent living including adequate accessible and adaptable housing and related support | 198 | Support people to live well with dementia by providing high quality compassionate care for people with dementia and their carers in their own home or hospital, including piloting different approaches to providing care and support for people with dementia in their own homes as funding allows |  | Social Care – Older People | ü | ü | ü | ü | ü | ü | ü | ü |  | Ongoing
Objective 3: We will take action to improve the Living Standards of people disadvantaged by their protected characteristics | Priority Area 3.2: Support disabled people, children and older people's right to independent living including adequate accessible and adaptable housing and related support | 199 | Work with partners to increase the supply and quality of appropriate accommodation in the independent care sector (e.g. residential & nursing care homes) |  | Social Care | ü | ü | ü | ü | ü | ü | ü | ü | ü
Objective 3: We will take action to improve the Living Standards of people disadvantaged by their protected characteristics | Priority Area 3.2: Support disabled people, children and older people's right to independent living including adequate accessible and adaptable housing and related support | 200 | Work with service users, families, carers, staff and the third sector to enable people who have profound and multiple learning disabilities to develop to their full potential |  | Social Care – Disability Service | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 3: We will take action to improve the Living Standards of people disadvantaged by their protected characteristics | Priority Area 3.2: Support disabled people, children and older people's right to independent living including adequate accessible and adaptable housing and related support | 201 | Disability Occupational Therapy services will provide timely assessments of the needs of disabled people, ensuring that they have access to equipment that can support their independence and working with Housing Adaptations and the Registered Social Landlords to ensure that individuals are appropriately accommodated in housing that meets their specific needs |  | Social Care - Disability Service |  | ü |  |  |  | ü |  |  |  | Ongoing
Objective 3: We will take action to improve the Living Standards of people disadvantaged by their protected characteristics | Priority Area 3.2: Support disabled people, children and older people's right to independent living including adequate accessible and adaptable housing and related support | 202 | People with learning disabilities and their parents/carers will have access to good, consistent and accessible information and advice to proactively plan for the future |  | Social Care – Disability Service | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 3: We will take action to improve the Living Standards of people disadvantaged by their protected characteristics | Priority Area 3.2: Support disabled people, children and older people's right to independent living including adequate accessible and adaptable housing and related support | 203 | Promote “recycle schemes” for community equipment, encouraging returns for adaptations to continue recycling above the 70% Key Performance Indicator standard |  | Social Care – Community Wellbeing | ü | ü | ü | ü | ü | ü | ü |  |  | Ongoing
Objective 3: We will take action to improve the Living Standards of people disadvantaged by their protected characteristics | Priority Area 3.5: Ensure that housing, homelessness and asylum services are inclusive of the specific needs of minority groups, including LGBTQ+ people, ethnic minority people and disabled people | 204 | Monitor the demand for adapted affordable housing to ensure new Social Housing meets the needs of disabled people |  | Regulatory & Housing (Housing) |  | ü | [7 empty] | Ongoing
Objective 4: We will improve Health, Wellbeing and Social Care outcomes | Priority Area 4.1: Ensure health and wellbeing needs of carers are met | 205 | Support young carers to achieve their potential |  | Social Care – Family Support & Intervention | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 4: We will improve Health, Wellbeing and Social Care outcomes | Priority Area 4.3: Evaluate progress on mental health to ensure we are meeting the needs of people with different protected characteristics | 206 | Work with partner agencies to support people with co-morbidities so that they can access specialist services as and when they need them, to ensure that their mental health diagnosis does not impede them from receiving physical health care. |  | Social Care – Vulnerable People | ü | ü | ü | ü | ü | ü | ü |  |  | Ongoing
Objective 4: We will improve Health, Wellbeing and Social Care outcomes | Priority Area 4.3: Evaluate progress on mental health to ensure we are meeting the needs of people with different protected characteristics | 207 | We will work with partners to ensure Conwy citizens have timely access to mental health assessment and support |  | Social Care – Vulnerable People | ü | ü | ü | ü | ü | ü | ü |  |  | Ongoing
Objective 4: We will improve Health, Wellbeing and Social Care outcomes | Priority Area 4.3: Evaluate progress on mental health to ensure we are meeting the needs of people with different protected characteristics | 208 | Build upon existing relationships with Mental Health colleagues to further enhance partnership working opportunities to underpin prevention of homelessness |  | Regulatory & Housing (Housing) | ü | ü | ü | ü | ü | ü | ü |  |  | Ongoing
Objective 4: We will improve Health, Wellbeing and Social Care outcomes | Priority Area 4.6: Address barriers to exercise and wellbeing | 209 | Promote the “Staying Well” programme of activities targeting specific issues for specific age groups |  | Social Care – Community Wellbeing | [5 empty] | ü |  |  |  | Ongoing
Objective 4: We will improve Health, Wellbeing and Social Care outcomes | Other actions on Health, Wellbeing and Social Care identified from consultation | 210 | Continue joint working with Children and Adolescent Mental Health Services (CAMHS) through delivery of a joint action plan |  | Social Care – Family Support & Intervention | ü | ü | ü | ü | ü | ü | ü |  | ü | Ongoing
Objective 5: We will improve Personal Security and Access to Justice | Priority Area 5.2: Work with North Wales partners to reduce incidents of Violence Against Women, Domestic Abuse and Sexual Violence (VAWDASV) | 211 | Continue to support the International Domestic Abuse awareness raising day on 25th November |  | Regulatory & Housing (Community Safety) | ü | ü | ü | ü | ü | ü | ü | ü | ü | Annually
Objective 5: We will improve Personal Security and Access to Justice | Priority Area 5.2: Work with North Wales partners to reduce incidents of Violence Against Women, Domestic Abuse and Sexual Violence (VAWDASV) | 212 | Work with MARRAC to manage the levels of repeat victims of Domestic Abuse |  | Regulatory & Housing (Community Safety) / Social Care | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 5: We will improve Personal Security and Access to Justice | Priority Area 5.3: Improve awareness of personal safety and safeguarding responsibilities | 213 | Support vulnerable people to prevent them becoming victims of crime |  | Regulatory & Housing (Community Safety) | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 5: We will improve Personal Security and Access to Justice | Priority Area 5.3: Improve awareness of personal safety and safeguarding responsibilities | 214 | Work in partnership to reduce youth offending and adult offending |  | Regulatory & Housing (Community Safety) | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 5: We will improve Personal Security and Access to Justice | Priority Area 5.3: Improve awareness of personal safety and safeguarding responsibilities | 215 | Continue to raise awareness of fraud and scams aimed at vulnerable members of the public |  | Regulatory & Housing (Regulatory) | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 5: We will improve Personal Security and Access to Justice | Priority Area 5.3: Improve awareness of personal safety and safeguarding responsibilities | 216 | Increase awareness of children, young people and adults of safe, healthy and equal relationships |  | Regulatory & Housing (Community Safety) | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 5: We will improve Personal Security and Access to Justice | Priority Area 5.3: Improve awareness of personal safety and safeguarding responsibilities | 217 | We will continue to work with partners across sectors to contribute to the delivery of the regional Vulnerability and Exploitation Plan. Locally we are continually improving our knowledge and practice in targeting / reducing exploitation |  | Social Care – Children Families and Safeguarding | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 5: We will improve Personal Security and Access to Justice | Priority Area 5.3: Improve awareness of personal safety and safeguarding responsibilities | 218 | Continue to train staff and raise awareness that safeguarding is everyone’s responsibility | Corporate Plan 2022-2027 | Social Care | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 5: We will improve Personal Security and Access to Justice | Priority Area 5.3: Improve awareness of personal safety and safeguarding responsibilities | 219 | Undertake activities to promote National Safeguarding Week (e.g. 7 minute briefings shared with all CCBC employees; engagement in regional and national safeguarding events) |  | Social Care | ü | ü | ü | ü | ü | ü | ü | ü | ü | Annually
Objective 6: Increase Access to Participation and improve diversity in decision making | Priority Area 6.1: Increase awareness of the importance of diversity in political representation and decision making bodies | 220 | Co-option onto Council committees will be considered where permissible and appropriate to ensure a diverse balance of the committee. Member champions representing carers, older people, mental health, disability as well as the Democracy and Governance portfolio holder covering Equalities, will be consulted as part of the normal decision making process |  | Law and Governance | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 6: Increase Access to Participation and improve diversity in decision making | Priority Area 6.2: Ensure engagement is inclusive to provide a sense of belonging and community | 221 | Meet annually with Conwy Deaf Translation Support Service (CTDSS) and Vision Support Sight Loss Group to feedback on progress on Equality Objectives |  | People and Performance |  | ü | [7 empty] | Annually
Objective 6: Increase Access to Participation and improve diversity in decision making | Priority Area 6.2: Ensure engagement is inclusive to provide a sense of belonging and community | 222 | Continue to work towards closing gaps in the equality monitoring data we collect from service users within all our services and during engagement, ensuring that the data collected is used to remove barriers and demonstrate that services are inclusive |  | All Services | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 6: Increase Access to Participation and improve diversity in decision making | Priority Area 6.3: Access to services should be supported by appropriate language support, including Welsh, British Sign Language and other languages | 223 | Continue the provision of BSL interpreter real-time service |  | Economy & Culture |  | ü | [7 empty] | Ongoing
Objective 6: Increase Access to Participation and improve diversity in decision making | Priority Area 6.3: Access to services should be supported by appropriate language support, including Welsh, British Sign Language and other languages | 224 | Ensure that services commissioned by the council (where appropriate) take into account the needs of the deaf community / equality of access |  | All Services |  | ü | [7 empty] | Ongoing
Objective 6: Increase Access to Participation and improve diversity in decision making | Priority Area 6.3: Access to services should be supported by appropriate language support, including Welsh, British Sign Language and other languages | 225 | Continue to run regular Sensory Impairment Awareness training and promote to front line staff |  | People and Performance |  | ü | [7 empty] | Ongoing
Objective 6: Increase Access to Participation and improve diversity in decision making | Other actions on Participation and diversity in decision making identified from consultation | 226 | Provide customer access and assistance to information and sign-posting through Culture, Library and Information services |  | Economy & Culture | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 6: Increase Access to Participation and improve diversity in decision making | Other actions on Participation and diversity in decision making identified from consultation | 227 | Continue to develop resilience of the Home and Mobile Library Service as a key means to ensure equality of access to Council services and information for people living in remote areas, and as a tool for combatting loneliness and social isolation |  | Economy & Culture |  | ü |  |  |  | ü |  |  |  | Ongoing
Objective 7: Tackle socio-economic disadvantage by offering inclusive services to minimise inequalities of outcome | Priority Area 7.2: Address anti-social behaviour | 228 | Reduce crime, anti-social behaviour and ensure public safety with CCTV |  | Regulatory & Housing (Regulatory) | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 7: Tackle socio-economic disadvantage by offering inclusive services to minimise inequalities of outcome | Priority Area 7.2: Address anti-social behaviour | 229 | Continue to work with our partners through the Community Safety Partnership to promote and sustain the fact that Conwy is a safe county. |  | Regulatory & Housing (Community Safety) | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 7: Tackle socio-economic disadvantage by offering inclusive services to minimise inequalities of outcome | Priority Area 7.3: Remove barriers experienced by people due to socio-economic disadvantage | 230 | Raise awareness of ability to claim for housing benefit and council tax benefit on-line and for landlords to access benefit data via the web |  | Revenues & Benefits | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 7: Tackle socio-economic disadvantage by offering inclusive services to minimise inequalities of outcome | Priority Area 7.3: Remove barriers experienced by people due to socio-economic disadvantage | 231 | Ensure when delivering our Events Strategy that we offer and/or support a wide range of events and activities which cater for the whole population |  | Economy & Culture | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing