## Action Plan
DRAFT Strategic Equality Plan - Action Plan 2020 - 2024
Please Note: Some actions will be relevant under more than one objective but will only be shown once on the Action Plan under the most relevant heading. Between 2020 and 2024, we anticipate that the financial constraints placed upon Conwy County Borough Council, along with all other public bodies in Wales, will be even greater than they have been in the previous 4 years. Whilst what we have set out in the Action Plan attached to our revised Strategic Equality Plan is believed to be achievable at the time of writing, we will continuously have to prioritise and reprioritise what we do to survive these ever increasing pressures.
Objective 1 : Outcomes in Education attainment and Wellbeing in Schools are Improved
Priority Area 1.1: Address attainment gaps for children and young people to maximise their potential
Protected Characteristic
| Action | Responsibility | Race | Disability | Sex | Gender Reassignment | Sexual Orientation | Age | Religion/Belief | Marriage/ Civil Partnership | Pregnancy/ Maternity | Complete by
1.1.1 | Local Authority (LA) and GwE (School Effectiveness and Improvement Service for North Wales) will work closely with schools to collate performance data on all groups of learners and where possible those with protected characteristics to inform school development plans and GwE/LA joint business plans. | Education | ü | ü | ü | ü | ü | ü | ü |  | ü | Annually
1.1.2 | Review and develop suitable provision for vulnerable learners in order to ensure that appropriate and cost effective pathways are available to meet the duties under the Additional Learning Needs Act. | Education | ü | ü | ü | ü | ü | ü | ü |  | ü | Review 31/08/2020
1.1.3 | Review ALN Teaching Assistant Provision in Conwy | Education | ü | ü | ü | ü | ü | ü | ü |  | ü | 2020-08-31
1.1.4 | Work with schools to improve results at each key stage of education. We will focus support on groups of learners such as Looked After Children, those on free school meals as well as challenging our high achievers. | Education | ü | ü | ü | ü | ü | ü | ü |  | ü | 2022-03-31
1.1.5 | Report progress on figures for pupils who are not in Education, Employment, or Training (NEET) by academic year | Education | ü | ü | ü | ü | ü | ü | ü | ü | ü | Annually
1.1.6 | Upgrade school technology infrastructure to offer greater opportunities to pupils | Information Technology | ü | ü | ü | ü | ü | ü | ü |  | ü | 30/9/2020
1.1.7 | Work with schools to implement the digital competency framework | Education | ü | ü | ü | ü | ü | ü | ü | ü | ü | 30/9/2020
1.1.8 | Young people up to the age of 25 are able to access education provision locally to meet their additional learning needs | Social Care / Education | ü | ü | ü | ü | ü | ü | ü | ü | ü | 30/09/2021
Priority Area 1.2: Reduce high exclusion rates for disabled and mixed race children
1.2.1 | Work closely with GwE when School Support Plans are being developed to ensure permanent and temporary exclusions are reviewed by protected characteristic and issues identified and addressed through the business planning cycle. Evaluate and analyse permanent and temporary exclusions data to consider actions to ensure there is no adverse impact on particular protected groups, eg, disabled pupils. Actions to include consideration of the wellbeing of excluded pupils and the introduction of a temporary exclusion appeal process. | Education | ü | ü | ü | ü | ü | ü | ü |  | ü | Review 31/08/2020
Priority Area 1.3: Collate bullying data by protected characteristic to enable each school to identify relevant objective(s)
1.3.1 | Develop and co-ordinate online reporting tool for the collection of bullying data in schools and to identify bullying stats against equality categories utilising WG toolkit and HwB | Education | ü | ü | ü | ü | ü | ü | ü |  | ü | 31/12/2020
1.3.2 | To work in partnership with Conwy schools and partners to implement the All Wales Anti Bullying Guidance. | Education | ü | ü | ü | ü | ü | ü | ü |  | ü | 01/09/2020
1.3.3 | Work closely with GwE when School Support Plans are being developed to ensure bullying actions are fed into the business planning cycle and this information is reported on in the GwE annual report. | Education | ü | ü | ü | ü | ü | ü | ü |  | ü | Ongoing
1.3.4 | Work with Show Racism the Red Card once clearer bullying data has been identified to determine priority schools for further action | Education | ü | ü | ü | ü | ü | ü | ü |  | ü | Ongoing
1.3.5 | Roll out the Gender Identity Policy and Implementation Guidance to all schools in Conwy and review policy implementation as per policy | Education / Community Development Services | ü | ü | ü | ü | ü | ü | ü |  | ü | 31/12/2020
1.3.6 | We will work with other North Wales Local Authorities to share best practice and learn from each other in seeking to address identity based bullying in schools | Corporate Human Resources in liaison with North Wales Public Sector Equality Network | ü | ü | ü | ü | ü | ü | ü |  | ü | 31/12/2021
Priority Area 1.4: Tackle gender segregation by improving representation of girls and women on STEM courses (Science, Technology, Engineering and Maths) and expanding range of subject choice
1.4.1 | As part of the self-evaluation and improvement planning process for each school, ensure that schools governors and business managers include themes for self-audit around Education Equality Objective Priorities (ie, attainment by protected characteristic, exclusions, identity based bullying, STEM) on a regular basis | Education | ü | ü | ü | ü | ü | ü | ü |  | ü | 2020-2024
1.4.2 | Continue to Run Take pART! which now incorporates arts and science with involvement of more organisations to extend the experience, eg, Techniquest (planetarium), the Big Learning Company (engineering and lego), Rolls Royce, Major Tim Space (science drop in sessions) – all projects to teach science through innovative means, eg, the project on “dark skies” works with an astronomer and physicist – encouraging young people to become dark skies ambassadors for the area | Venue Cymru | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2020-2024
1.4.3 | Promote the availability of work experience placements on technical work placements | ERF, Venue Cymru, IT, Corporate HR | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing 2020-24
1.4.4 | Deliver the STEM Gogledd project (Lead by Gwynedd CC) - to increase the take up and attainment in STEM subjects amongst 11-19 year olds in North West Wales through a range of interventions that will compliment but not duplicate mainstream services | Education / Community Development Services | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/12/2022
1.4.5 | Introduce annual checks to remind parents and Education about Free School Meals and other benefits parents are entitled to claim to ensure take up for those eligible | Revenue & Benefits | ü | ü | ü | ü | ü | ü | ü | ü | ü | Annually in December
1.4.6 | All schools in Conwy have a Young Ambassador programme that seeks to achieve Conwy’s A.I.M (Aspire, Inspire, Motivate) | Community Development Services | ü | ü | ü | ü | ü | ü | ü |  | ü | Ongoing
Priority Area 1.5: Address Mental Health for pupils in Schools
1.5.1 | We will focus on Adverse Childhood Experiences and provide support to parents through multi agency approaches | Social Care | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/03/2022
1.5.2 | Extend the Healthy Image Project (HIP) into schools, funded by an increase in WG grant for the next 3 years | Community Development Services | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/03/2022
1.5.3 | Apply for further funding from Children in Need to continue to support the work of “Create” funded through Conwy arts trust and Children in Need. Create is an arts group for 12-16 year olds that meets every week, to improve mental health and coping through the arts. Participants have to be referred by a mental health practitioner. The group also supports LGBTQ issues, particularly coping with family relationship difficulties as a result of LGBTQ. This work involves Education Counsellors and sessions are supported by a Sessional Support Worker. The value of this work is assessed in partnership with CAMHS using their score charts to work with attendees which shows week on week increases in wellbeing of participants. | Venue Cymru | ü | ü | ü | ü | ü | ü | ü |  | ü | 31/12/2020
1.5.4 | Provide free spaces for our Looked After Children at our Creative Arts groups which are also attracting young carers, eg, vertical dance classes | Venue Cymru | ü | ü | ü | ü | ü | ü | ü |  | ü | Ongoing
1.5.5 | Seek funding to continue “Create” – a group which meets weekly to support known mental health issues including suicidal thoughts and supporting young people with LGBTQ issues in partnership with youth work leaders supported by CAMHS | Venue Cymru | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
1.5.6 | Work to get the balance right—as well as being IT literate, young people need to be able to play and be physically literate. We will look at ways to help reduce childhood obesity and improve emotional health | All Services | ü | ü | ü | ü | ü | ü | ü |  | ü | 31/03/2022
1.5.7 | Advise, challenge and support primary schools to deliver a broad and balanced range of activities, to include the Daily Mile | Community Development Services | ü | ü | ü | ü | ü | ü | ü |  | ü | 31/03/2022
1.5.8 | Support secondary schools in delivering a broad and balanced range of extra-curricular physical activities, informed and planned by the Schools Sport Council | Community Development Services | ü | ü | ü | ü | ü | ü | ü |  | ü | 31/03/2022
1.5.9 | Continue joint working with Children and Adolescent Mental Health Services (CAMHS) through delivery of a joint action plan | Social Care – Family Support & Intervention | ü | ü | ü | ü | ü | ü | ü |  | ü | Ongoing
1.5.10 | To sustain and develop a Conwy wide whole school approach to mental and emotional wellbeing in line with the Mind Over Matter Report, in partnership with CAMHS and Public Health, we will roll out 5 Ways to Wellbeing Train the Trainer Training to upskill school based staff to become 5 Ways to Wellbeing Champions in all Conwy primary and secondary schools. | Education | ü | ü | ü | ü | ü | ü | ü |  | ü | Review 31/08/2020
1.5.11 | Maintain and quality assure the delivery of Seasons for Growth in Conwy School by recruiting additional trained mentors to provide one to one mentoring support for Seasons for Growth Companions, helping them to confidently plan, recruit, deliver and evaluate the delivery of Seasons for Growth in their respective schools. | Education | ü | ü | ü | ü | ü | ü | ü |  | ü | Review 31/08/2020
1.5.12 | Roll out of Friends for Life Programme in Conwy Schools, which focuses on the prevention of anxiety for children and young people, and early intervention for those with emerging difficulties and / or at high risk of developing anxiety in the future. The project will enhance the skills of the workforce to deliver the programme for children and young people in school and community settings. | Education | ü | ü | ü | ü | ü | ü | ü |  | ü | Review 31/08/2020
Priority Area 1.6: Other actions on Education identified from consultation
1.6.1 | We will introduce a consistent assessment of School Equality Plans through the School Management Review process | Education | ü | ü | ü | ü | ü | ü | ü |  | ü | 31/12/2020
1.6.2 | Work with GwE to ensure that schools when producing their School Development Plans meet the requirements of the Public Sector Equality Duty including annual reporting on progress | Education | ü | ü | ü | ü | ü | ü | ü |  | ü | Ongoing
1.6.3 | Ensure when building and renovating schools in Conwy as part of the 21st century schools modernisation programme, they are fully accessible | Education | ü | ü | ü | ü | ü | ü | ü |  | ü | Ongoing until 2024
1.6.4 | Review provision for managing LGBTQ issues in schools | Education | ü | ü | ü | ü | ü | ü | ü |  | ü | Review 31/8/2020
1.6.5 | Ensure reasonable adjustments are made for parents attending schools/parents evenings (including language provision, BSL) | Education | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing until 2024
1.6.6 | Schools to consider how they will accommodate temporary physical access issues for pupils with short term disabilities, eg, crutches, wheelchair | Education | ü | ü | ü | ü | ü | ü | ü |  | ü | Ongoing until 2024
Objective 2 : We will take action to ensure we are an equal opportunities employer and reduce pay gaps
Priority Area 2.1: Address gender, ethnicity and disability pay differences
2.1.1 | Undertake Equal Pay Audit and amend frequency and reporting arrangements in line with revised legislation and guidance (continue to report pay gaps for gender, ethnicity, disability and age in SEP Annual Report until then) | Corporate Human Resources | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2021-03-31
2.1.2 | Identify actions from Equal Pay Audit where there are gaps above 5% in line with EHRC guidance and publish actions and outcomes in the SEP Annual Report each year | Corporate Human Resources | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
2.1.3 | When the next Staff Survey is carried out, include a section to seek feedback around the pay gap and job segregation issues and any follow-on actions to be included in the following Equal Pay Audit report | Corporate Human Resources | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2021-12-31
2.1.4 | Publish gender pay gap on Gov.UK website | Corporate Human Resources | ü | ü | ü | ü | ü | ü | ü | ü | ü | Annually
2.1.5 | Review whether there are any unexpected patterns for staff working unsociable hours relating to their protected characteristic as part of the Equal Pay Audit | Corporate Human Resources | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2021-03-31
Priority Area 2.2: Review our flexible working practices to ensure equal opportunities at all levels
2.2.1 | We will review our Flexible Working Policy, Recruitment Policy and job advert process to consider a range of flexible working options | Corporate Human Resources | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/12/2022
2.2.2 | Review our other flexible working and Family Friendly policies to ensure they remain sufficiently flexible whilst achieving corporate objectives and that terminology is appropriate and avoids stereotypical inferences | Corporate Human Resources | ü | ü | ü | ü | ü | ü | ü | ü | ü | Before 31/3/2024
2.2.3 | We will remind managers and staff about the flexible options our policies offer and ensure a greater understanding across the organisation when we roll out revised policies | Corporate Human Resources | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/12/2022
2.2.4 | Raise awareness of the facilities and activities available to parents in Conwy County that Council staff can access, including for non-office based staff | Social Care – Community Wellbeing | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Priority Area 2.3 : Ensure effective policies to prevent and respond to sexual harassment
2.3.1 | Review our current Harassment Policy to ensure it sufficiently deals with the subject of Sexual Harassment following the Government consultation and forthcoming recommendations and guidance, ensuring a support mechanism is included for victims. | Corporate Human Resources | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/12/2021
2.3.2 | Provide training for managers on handling harassment allegations with roll-out of revised policy | Corporate Human Resources | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/12/2022
2.3.3 | Undertake a review of the Violence Against Women, Domestic Abuse and Sexual Violence Policy | Corporate Human Resources | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/12/2020
2.3.4 | Review our Grievance Policy to ensure it sufficiently deals with the subject of Sexual Harassment allegations | Corporate Human Resources | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/12/2021
2.3.5 | Review our current Bullying Policy | Corporate Human Resources | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/12/2022
Action Area 2.4 : Review Pregnancy and Maternity Provision in the Workplace
2.4.1 | Review and revise the Corporate Policies for Maternity, Breastfeeding and Adoption into a combined policy, also incorporating Shared Parental Leave, to ensure they are relevant and up to date in respect of legislation and implement the 6 areas of action outlined in “Pregnancy and Maternity Discrimination in the workplace: Recommendations for change” report and adopt the Working Forward pledge | Corporate Human Resources | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/12/2020
2.4.2 | Undertake a survey of staff who have been on maternity leave in the previous 3 years to evaluate their experience and take action as necessary | Corporate Human Resources | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/12/2020
2.4.3 | Develop a Fostering Policy | Corporate Human Resources | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/12/2020
2.4.4 | To develop a guidance document on Menopause | Corporate Human Resources | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/12/2020
Priority Area 2.5 : Ensure any use of insecure employment contracts (e.g. casuals) adequately protects their rights as workers
2.5.1 | Review Casual Worker Policy to ensure consistency of treatment between workers and that it adequately protects their rights. | Corporate Human Resources | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/12/2021
2.5.2 | Develop a policy covering the employment arrangements and pay for work placement students across Conwy Council | Corporate Human Resources HR | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/12/2022
2.5.3 | Review our Volunteers Policy | Corporate HR | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/12/2023
2.5.4 | Implement the Ethical Procurement Policy and raise awareness , particularly ensuring procurement from organisations who ensure ethical employment practices including fair practices for insecure employment and the rights of workers are not eroded | Audit & Procurement | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/12/2020
2.5.5 | Encourage other employers who we commission work to, to implement a recruitment process that anonymises applicants identity from the initial shortlisting stage of the recruitment process to remove bias about suitability based on name, gender, age, etc, to maximise fair selection procedures | Audit & Procurement | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/12/2020
Priority Area 2.6: Increase number of disabled people in work
2.6.1 | Develop an action plan to work towards Disability Confident Leader | Corporate Human Resources | ü | ü | ü | ü | ü | ü | ü | ü | ü | 30/9/2022
2.6.2 | Undertake consultation to consider if it would be appropriate to introduce a Reasonable Adjustments Disability Passport | Corporate Human Resources | ü | ü | ü | ü | ü | ü | ü | ü | ü | 30/9/2022
2.6.3 | Sign up to the Time to Change pledge, a campaign to end stigma and discrimination faced by people with mental health problems and to improve attitudes and change behaviour towards mental health in society. | Corporate Human Resources | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/12/2020
2.6.4 | Provide written feedback for disabled applicants who don’t get shortlisted or employed to explain why and explain the process (provide training for managers) | All services | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
2.6.5 | Consider adoption of the Same but Different pledge: “Rare Aware Charter” to create a supportive working environment for employees who have a rare disease or have a close family member affected | Corporate Human Resources | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/12/2020
2.6.6 | Review options for sharing vacancies with disability groups and organisations | Corporate Human Resources | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/12/2020
2.6.7 | Pilot opportunities for people with disabilities to work alongside parks and gardens staff in the community | Social Care – Disability / ERF | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/12/2020
2.6.8 | Investigate further the opportunity to participate in Project SEARCH, a transition to work programme for young people aged 17-24 with learning disabilities and/or autism, a business led collaboration supported by education providers and supported employment providers to develop skills for employment that are transferable across sectors and employers | Corporate Human Resources and Social Care – Disability Service | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/12/2020
Priority Area 2.7: Reduce Gender Segregation (the unequal distribution of men and women working in traditionally gender specific roles)
2.7.1 | Produce a guide on avoiding biased and stereotypical language in the recruitment and other employment processes | Corporate Human Resources | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/12/2020
2.7.2 | Revise our Job Evaluation scoring form so that Mini Panel members when scoring posts, also check for gender stereotyping and other biased language in job titles, job descriptions and person specifications. | Corporate Human Resources | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2020-12-31
2.7.3 | Implement a mechanism for reviewing the wording on Job Advertisements to ensure they are free from gender stereotyping and other biased language | Corporate Human Resources | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/12/2020
2.7.4 | Develop and implement a plan to improve Attraction, Recruitment and Retention of the Social Care Workforce | Social Care | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2021-12-31
2.7.5 | Support cross-Council initiatives to raise awareness of Engineering and Technical opportunities and career paths in STEM subjects at school, further education and other public events such as careers fairs, Wales GB, Take pART, RGC (North Wales Rugby) | ERF, Corporate HR, Education, CDS, Marketing, Venue Cymru | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing 2020-24
Priority Area 2.8: Improve participation of women, ethnic minorities and disabled people across apprenticeships
2.8.1 | Support skills development including apprenticeships to equip people to be ready for work opportunities in the region | Corporate Improvement & Development | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/03/2022
2.8.2 | Expand the opportunities for work placements and work experience for people from different Protected Characteristics | All Services | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
2.8.3 | Collect equality data from work placement applications | Corporate Human Resources | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2021-12-31
2.8.4 | Expand the opportunities to increase participation of under-represented groups in Apprenticeships | All Services employing Apprentices | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
2.8.5 | Consider and implement appropriate initiatives within the council for work experience and apprenticeships for our Looked After Children | Corporate Human Resources | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
2.8.6 | Develop a Social Care Apprenticeship Scheme | Social Care | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2022-12-31
Priority Area 2.9: Consider the use of positive action measures in recruitment campaigns where specific groups are under-represented
2.9.1 | Review our recruitment process to include more information about what we do to encourage a wider section of our community into work | Corporate Human Resources | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/12/2022
2.9.2 | We will continue to improve our position on equality data collection from staff, encouraging disclosure so that we can make better use of positive action measures | Corporate Human Resources | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
2.9.3 | Develop and run pre-employment workshops to help those furthest from employment understand the recruitment process, employer expectations and employment rights | Corporate HR with NWPSEN | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2021-12-31
2.9.4 | Review training and development opportunities for under-represented groups at senior levels within the workforce with a view to equipping them for internal progression | Corporate Human Resources | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2022-12-31
2.9.5 | Review coaching and mentoring schemes or leadership development programmes for women | Corporate Human Resources | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/12/2022
2.9.6 | Review and develop employability activity that supports social care clients to get as close to the labour market as possible | Social Care – Community Wellbeing | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2020-09-30
2.9.7 | Where we have vacancies and the staff make up is not representative we will seek to use positive action measures with a view to recruiting a more diverse workforce | All services | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Priority Area 2.10: Other actions on Employment and Pay identified from consultation
2.10.1 | Improve accessibility to our on-line recruitment by simplifying the application process to meet the needs of all levels of job applicant and disabled people | Corporate Human Resources | ü | ü | ü | ü | ü | ü | ü |  |  | 31/1/2021
2.10.2 | Communicate the support mechanisms and tools available for managers to cascade to staff when managing staff reductions/ increased workload to ensure positive mental wellbeing of their teams when dealing with change | Corporate Human Resources | ü | ü | ü | ü | ü | ü | ü |  | ü | 2021-12-31
2.10.3 | Led by Grwp Llandrillo Menai, deliver the ADTRAC project to support those identified as NEET (Not in Education Employment or Training) Aged 16-24 to overcome barriers and engage in skills and employment opportunities | Community Development Services | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2020-08-31
2.10.4 | Continue to deliver Communities for Work (C4W) Welsh Government projects targeting those aged 25+ economically inactive or long term unemployed and NEETS aged 16-24, to overcome barriers to skills and employment. | Community Development Services | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2022-06-30
2.10.5 | We will develop a framework for employability projects and initiatives within the Youth Service, responding to the substantial increase in the WG Youth Support Grant, developing and implementing a range of initiatives in partnership with Education (Education and Progression Co-ordinator and Housing) | Community Development Services | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/3/2022
2.10.6 | (CHR) Develop a Transgender Policy | Corporate Human Resources | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2020-07-31
2.10.7 | Continue to work with JobCentre Plus to provide quarterly Provider Events for job seekers to access advice and support about training, volunteering and work opportunities | Community Development Services | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 3 : We will take action to improve the Living Standards of people disadvantaged by their protected characteristics
Priority Area 3.1: Take action to address disproportionate negative impact on people with different protected characteristics
3.1.1 | Ensure Equality Impact Assessments are undertaken on policies and practices and action is taken to address where negative impact is identified | All Services | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
3.1.2 | Continue to be a member of “Hynt” Wales scheme – for disabled people to use their Hynt card around Wales (offers attendance of a companion for free,) and access needs are registered on box office systems to avoid repeating any special facility requirements every time they make a booking. | Venue Cymru |  | ü |  |  |  | ü |  |  |  | Ongoing
3.1.3 | Continue to provide relaxed performances, subtitled film showings in Colwyn Theatre, Audio described films, signed and audio described performances in Venue Cymru when there are week-long shows running | Venue Cymru |  | ü |  |  |  | ü |  |  |  | Ongoing
3.1.4 | Continue to provide monthly dementia screenings with low price tickets and the Conwy staff choir perform in the interlude | Venue Cymru | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
3.1.5 | Establish a regular dementia choir in partnership with Forget-me-Not choir | Venue Cymru | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/12/2020
3.1.6 | Establish a regular Board Games event for older people and people at risk of isolation | Venue Cymru |  | ü | ü |  |  | ü |  |  |  | 31/12/2020
3.1.7 | Work in partnership to develop an integrated and holistic approach to tackling the underlying causes of homelessness, through joined up service delivery, joint protocols and effective referral arrangements | Regulatory & Housing | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
3.1.8 | Undertake an awareness raising campaign in relation to homeless prevention, and specifically Conwy Housing Solutions | Regulatory & Housing | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
3.1.9 | Work in partnership with Children's Services to develop housing and support options that avoid the need to place 16 and 17 year olds in Bed and Breakfast | Regulatory & Housing | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
3.1.10 | Ensure dedicated resources are in place targeted at tackling homelessness amongst prison leavers | Regulatory & Housing | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
3.1.11 | Work with partners to increase the supply and quality of appropriate accommodation in the independent care sector (e.g. residential & nursing care homes) | Social Care | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/03/2022
3.1.12 | Welfare Reform Project – to raise awareness of Universal Credit and ensure the protection of specific groups (eg, mixed age couples, single parents, disability) to maximise the benefit claims they are entitled to | Revenues and Benefits | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/12/2023
3.1.13 | Raise awareness of ability to claim for housing benefit and council tax benefit on-line and for landlords to access benefit data via the web | Revenues and Benefits | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Priority Area 3.2: Support disabled people’s right to independent living including adequate accessible and adaptable housing and related support
3.2.1 | Work with our partners to develop community resource teams to support older people who need support to stay independent within their own homes | Social Care – Older People | ü | ü | ü | ü | ü | ü | ü | ü |  | Ongoing
3.2.2 | Pilot a different approach to providing care and support for people with dementia in their own homes | Social Care – Older People | ü | ü | ü | ü | ü | ü | ü | ü |  | Ongoing | Provide directed equality training for staff designing specific services which will affect different groups differently, eg, IT staff designing webpages
3.2.3 | Support people to live well with dementia by providing high quality compassionate care for people with dementia and their carers in their own home or hospital | Social Care – Older People | ü | ü | ü | ü | ü | ü | ü | ü |  | Ongoing
3.2.4 | Agree action plan including Service area specific performance indicators to increase take up of Direct Payments | Social Care | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/3/2021
3.2.5 | Deliver on Disabilities Accommodation Development project for Maelgwyn for social housing and housing for care leavers | Social Care | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/12/2020
3.2.6 | Explore extra care housing opportunities in the Colwyn Bay area (Project Paradise) | Social Care | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/07/2022
3.2.7 | Development of Bron y Nant, Dinerth Road, Colwyn Bay into a Disability Respite Centre with Shop and Café (Project Crystallise) | Social Care | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/03/2021
3.2.8 | We will implement the Accommodation Strategy for Vulnerable People Service to ensure access to suitable accommodation | Social Care | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
3.2.9 | Continue to implement Part M of the Building Regulations which requires housebuilders to construct new housing to standards that enable disabled people, particularly wheelchair users and those with mobility or ambulant impairments, to visit a house and have access to a ground floor living space and toilet | Regulatory - Planning Policy |  | ü |  |  |  | ü |  |  |  | Ongoing
3.2.10 | To construct adapted affordable housing to meet the needs of disabled people in line with the Council’s Local Housing Market Assessment | Regulatory - Planning Policy |  | ü |  |  |  | ü |  |  |  | Ongoing
3.2.11 | Ensure an effective and efficient Disabled Facilities Grant (DFG) application process. | Regulatory - Housing |  | ü |  |  |  | ü |  |  |  | Ongoing
3.2.12 | Explore the potential for the Housing Improvements Team to undertake Healthy Homes checks, supported by Warm Wales | Regulatory - Housing | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
3.2.13 | Deliver the Sub-Regional Children’s Residential Assessment Centre Project in partnership with Denbighshire and BCUHB where children can stay for up to 12 weeks to be assessed and have care and support plans in place to avoid them becoming looked after children. | Social Care | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/03/2021
3.2.14 | Provide support for vulnerable residents in Conwy to live independently in appropriate and suitable accommodation. | Regulatory - Housing | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
3.2.15 | Implement the recommendations from the Wales Audit Office Housing Adaptations report to include the development of shared Customer Care Standards for adaptations, a Customer Satisfaction form for customers to complete following an adaption and to review the process 6 months after implementation | Regulatory - Housing |  | ü |  |  |  | ü |  |  |  | 31/3/2021
3.2.16 | Ensure the housing needs of older people are fully understood and a range of housing options are available | Regulatory - Housing |  | ü |  |  |  | ü |  | ü |  | 31/12/2023
3.2.17 | Promote “recycle schemes” for community equipment, encouraging returns for adaptations to continue recycling above the 70% Key Performance Indicator standard | Social Care – Community Wellbeing | ü | ü | ü | ü | ü | ü | ü |  |  | Ongoing
3.2.18 | Maintain an efficient service in respect of enforcement of Planning and Building Control to keep communities safe | Regulatory – Planning | ü | ü | ü | ü | ü | ü | ü |  | ü | Ongoing
3.2.19 | Increase the supply of affordable housing which meets identified need and assists in mitigating the impact of the UK Government’s welfare reforms, focusing on the gaps in supply | Regulatory – Housing | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/03/2023
3.2.20 | Increase the supply of appropriate market housing which meets identified need | Regulatory – Planning | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/03/2022
3.2.21 | People are involved in developing and reviewing their own Personal Plans of Support | Social Care – Disability Service | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
3.2.22 | Work with service users, families, carers, staff and the third sector to enable people who have profound and multiple learning disabilities are able to develop to their full potential | Social Care – Disability Service | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
3.2.23 | People with disabilities living in the rural area have access to a project that supports them to be involved in their local community. | Social Care – Disability Service | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/12/2020
3.2.24 | People with learning disabilities and their parents/carers will have access to good, consistent and accessible information and advice to proactively plan for the future when the person loses their carer. | Social Care – Disability Service | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/12/2020
Priority Area 3.3: Better engagement with disabled people when renovating and designing buildings to ensure full accessibility
3.3.1 | Produce a guide for non-public organisations on disability access | Corporate HR with NWPSEN |  | ü |  |  |  | ü |  |  |  | 31/12/2021
3.3.2 | The relevant Project Board/Project Team will ensure that appropriate engagement involves disabled people at the initial design phase of projects for new build projects and renovations which will be open to the public | All Services |  | ü |  |  |  | ü |  |  |  | Ongoing
3.3.3 | When developing plans for phase 2 of development of Venue Cymru to consult with disability access group | Venue Cymru |  | ü |  |  |  | ü |  |  |  | 31/03/2021
3.3.4 | Develop a corporate policy on building repair and maintenance covering the need to ensure appropriate access issues are catered for | Environment, Roads & Facilities | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/3/2021
3.3.5 | Public Convenience Upgrades | Environment, Roads & Facilities | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/3/2021
Objective 4 : We will improve Health, Wellbeing and Social Care outcomes
Priority Area 4.1: Ensure health and wellbeing needs of carers are met
4.1.1 | We will undertake the actions set out in the North Wales Carers Strategy Action Plan. | Social Care – Community Wellbeing | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
4.1.2 | Undertake quarterly Carers Group Reviews internally to Conwy to reviews progress, service delivery, number of assessments and benchmark against statutory requirements covering all ages to determine appropriate actions | Social Care – Community Wellbeing | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
4.1.3 | We will undertake carer needs assessments under Social Services & Well-being Act (Wales) 2014 and review progress annually to Track the Act and assess our position and produce an annual report showing the gap analysis and required actions | Social Care – Community Wellbeing | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
4.1.4 | To support young carers to achieve their potential | Social Care – Family Support & Intervention | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
4.1.5 | Carers will have access to a range of flexible career breaks | Social Care – Disability Service | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/12/2020
4.1.6 | Continue to promote Foster Carer recruitment | Social Care | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Priority Area 4.2: Improve access to services for Gypsy and Traveller communities and improve engagement to develop trust
4.2.1 | Provide accommodation for the Gypsy and Traveller community in line with the assessment of need carried out to deliver a transit site for up to 7 pitches in the Deposit Replacement Local Development (RLDP). | Regulatory and Housing | ü | [8 empty] | 31/03/2023
4.2.2 | We will undertake health assessments in line with the Gypsy/Traveller Encampment protocol and make any health referrals as appropriate, depending on the circumstances. Where Gypsy/Traveller(s) are accessing medical treatment at a local surgery or hospital we may tolerate the encampment until the treatment has finished. We will also provide toilet facilities where this is identified as a health requirement as part of the assessment and we will report any safeguarding concerns using our usual reporting procedures. | Regulatory and Housing | ü | ü |  |  |  | ü |  |  |  | Ongoing
4.2.3 | Working collaboratively with the Gypsy/Traveller community and neighbouring authorities to update the Gypsy and Traveller Accommodation Needs Assessment (GTANA) | Regulatory and Housing | ü | ü |  |  |  | ü |  |  |  | 31/03/2023
4.2.4 | Working collaboratively with the Gypsy/Traveller community and neighbouring authorities to deliver any newly identified site requirements concluded in the updated GTANA through the Deposit Replacement Local Development (RLDP) | Regulatory and Housing | ü | [8 empty] | 31/03/2023
Priority Area 4.3: Increase uptake rates of people with learning disabilities taking up annual health checks
4.3.1 | Work with the regional Learning Disability Transformation Team Project Manager to continue to improve take up in Conwy of annual health checks through actions such as requiring the Residential Homes and Supported Living Providers to report on this as part of their performance | Social Care – Disability Service |  | ü |  |  |  | ü |  |  |  | 31/12/2020 and ongoing
Priority Area 4.4: Suicide prevention plan Talk to Me 2 is fully evaluated and new action plan to reduce suicide in middle aged men in Wales
4.4.1 | Support the delivery of the regional objectives as set out in the North Wales Suicide and self-harm prevention strategic plan (2018-21) which includes: Increase awareness and understanding of suicide and self-harm with the priority groups, eg, ‘Men in mid-life’ and veterans; to deliver appropriate responses to personal crises; support for those bereaved or affected by suicide and self-harm; reduce access to the means of suicide | Social Care – Vulnerable People | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/12/2021
4.4.2 | Be a key partner and stakeholder of the Regional suicide and self-harm prevention board in a coordinated response to a new/updated action plan of the Talk to Me 2 or subsequent policy | Social Care – Vulnerable People | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/12/2022
4.4.3 | Develop an action plan to target the improvement of mental wellbeing in farming communities, in particular with the impact of Brexit | Social Care – Vulnerable People | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/12/2020
4.4.4 | Promote the “staying well” programme of activities targeting specific issues for specific age groups | Social Care – Community Wellbeing | [5 empty] | ü |  |  |  | Ongoing
Priority Area 4.5: Evaluate progress on mental health to ensure we are meeting the needs of people with different protected characteristics
4.5.1 | Review our Commissioning Strategy and reinforce our commitment to supporting work around mental health | Social Care | ü | ü | ü | ü | ü | ü | ü |  |  | 31/12/2021
4.5.2 | We will work with partners to ensure Conwy citizens have timely access to mental health assessment and support | Social Care – Vulnerable People | ü | ü | ü | ü | ü | ü | ü |  |  | 31/03/2022
4.5.3 | Implement Early intervention and Prevention approach across Mental Health and Vulnerable people teams | Social Care – Mental Health | ü | ü | ü | ü | ü | ü | ü |  |  | 31/03/2022
4.5.4 | Build upon existing relationships with Mental Health colleagues to further enhance partnership working opportunities to underpin prevention of homelessness | Regulatory and Housing | ü | ü | ü | ü | ü | ü | ü |  |  | Ongoing
4.5.5 | We will explore successful initiatives (including our own) with other North Wales providers to look at alternative ways of supporting people in their mental wellbeing through the Arts | Venue Cymru | ü | ü | ü | ü | ü | ü | ü |  |  | Ongoing
4.5.6 | We will develop approaches to encourage people to take part in physical activity | All services | ü | ü | ü | ü | ü | ü | ü |  |  | 31/3/2022
4.5.7 | Co-produce mental health services in the community in partnership with commissioned stakeholder/focus groups to understand what an inclusive service would look like for LGBTQ groups, adults with autism and carers | Social Care – Vulnerable People | ü | ü | ü | ü | ü | ü | ü |  |  | 31/7/2020
4.5.8 | Work with people with co-morbidities so that they can access specialist services as and when they need them, to ensure that their mental health diagnosis does not impede them from receiving physical health care. | Social Care – Vulnerable People | ü | ü | ü | ü | ü | ü | ü |  |  | Ongoing
Priority Area 4.6: Use Social Model of Disability language
4.6.1 | Implement a Ten Top Tips guide on the Social Model of Disability and communicate this across Conwy Council to encourage the use of appropriate Social Model language in the delivery of our services | Corporate Human Resources |  | ü | [7 empty] | 31/12/2020
4.6.2 | Develop an e-learning module on the Social Model of Disability to roll out across CCBC | Corporate Human Resources |  | ü | [7 empty] | 31/12/2022
4.6.3 | Work with the Regional Learning Disability Transformation Team who is leading on values and culture which includes the social model of disability | Social Care – Disability Service |  | ü |  |  |  | ü |  |  |  | 31/12/2020
Priority Area 4.7: Implement specific awareness and support for people with neurological conditions
4.7.1 | Develop a Neurodiversity Policy and launch with awareness training for managers and staff | Corporate Human Resources |  | ü | [7 empty] | 31/12/2020
4.7.2 | Participate in the task and finish group considering the revised Autism Spectrum Disorder (ASD) Code of Practice which will sit under the Social Services and Wellbeing Act 2016, and work with the Conwy Denbighshire Stakeholder group to agree a new ASD local action plan for Conwy and Denbighshire | Social Care – Disability Service |  | ü | [7 empty] | 31/12/2020
Priority Area 4.8: Other actions on Health, Wellbeing and Social Care identified from consultation
4.8.1 | Develop new models to promote health & well-being so that people of all ages are less reliant on health and social care. We will do this by working collaboratively and looking at future trends. | Community Development Services | ü | ü | ü | ü | ü | ü | ü |  | ü | 31/3/2022
4.8.2 | Agree and implement a strategy to ensure the Disability Service is able to comply with Regulation 16 (1) ‘The personal plan must be reviewed as and when required but at least every 3 months’ | Social Care – Disability Service |  | ü |  |  |  | ü |  |  |  | Ongoing
4.8.3 | Ensure a sufficiently large, skilled, safe and focused workforce to promote the well-being of people with care and support needs | Social Care | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
4.8.4 | Launch and deliver a pathway into Step up to Care within Conwy County under 2 streams – targeted at people who are unemployed and full time education students already undertaking Social Care courses (including Social Care Administration as well as Social Workers) | Social Care | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/12/2021
4.8.5 | Support national “We Care” campaign to encourage more people into care work | Social Care | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/12/2021
4.8.6 | We will work to support the priorities of the Making Wales the best place in the world to grow older: Older Person’s Commissioner Strategy 2019-2022 | Social Care | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/12/2022
4.8.7 | Continue to develop ‘Dancing the Decades’ tour with Dawns i Bawb, touring care homes in Conwy County. ‘Dancing the Decades’ is an interactive performance which allows audience members to enjoy the show whilst also providing opportunities for them to participate. The work explore music, props, costumes and dance styles through the decades from 1920s to 1970s. | Community Development Services | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/12/2020
4.8.8 | Become a Dementia-friendly organisation | Social Care | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/12/2020
4.8.9 | Deliver the Imagine Colwyn Bay project targeted at younger people living with Dementia which has been identified as a gap in service provision and the projects will be themed according to 3 decades (60’s 70’s and 80’s). Artists will use objects from era to trigger discussion and creativity | Community Development Services | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2020-06-30
Objective 5 : We will improve Personal Security and Access to Justice
Priority Area 5.1: Work with our North Wales partners to increase confidence in Hate Crime awareness and reporting
5.1.1 | Explore the opportunity of developing a support network through our Equality Champions to support victims and witnesses of Hate Crime and other matters affecting people due to their protected characteristic, eg, Mate Crime, Elder Abuse, Domestic Abuse, etc | Corporate Human Resources | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/12/2020
5.1.2 | Ensure all services are aware of the Community Tension Monitoring form for front line staff and obtain feedback reports from the Community Cohesion Officers to consider appropriate actions | Regulatory & Housing (Community Safety) | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/12/2020
5.1.3 | Continue to raise awareness about Hate Crime, particularly during Hate Crime Awareness week with our North Wales partners | Corporate Human Resources with NWPSEN | ü | ü | ü | ü | ü | ü | ü | ü | ü | Annually
5.1.4 | Maintain links with the North Wales Community Cohesion team to support initiatives to improve community cohesion | Regulatory (Community Safety) & Corporate HR (Equalities) | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
5.1.5 | We will seek to tackle Modern Slavery and Human Trafficking with our North Wales partners and regularly review progress to determine our priority areas for action | Regulatory (Community Safety) | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Priority Area 5.2: Address VAWDASV by implementing relevant areas of the strategy by 2021
5.2.1 | Continue to deliver our commitment to ensure all staff are trained on VAWDASV and Safeguarding including new starters | Corporate Human Resources | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
5.2.2 | Support the International Domestic Abuse raising awareness day on 25th November | Regulatory & Housing | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing annually
5.2.3 | Work with MARRAC to manage the levels of repeat victims of Domestic Abuse | Regulatory & Housing | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
5.2.4 | Provide target hardening to vulnerable people, when victims or vulnerable people are identified, including for victims of domestic abuse | Regulatory & Housing | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
5.2.5 | Continue to fund 2 full time Independent Domestic Violence Advisor posts based with the North Wales Women's Centre in Rhyl and in Hafan Cymru in Conwy | Regulatory & Housing | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
5.2.6 | Support the actions on the Violence Against Women, Domestic Abuse and Sexual Violence Strategy ensuring that appropriate prevention programmes are delivered and implemented; survivors receive appropriate and timely support (including specialist support for BME women, disabled women, women with complex needs and children and young people) | Regulatory and Housing, Social Care - Safeguarding | ü | ü | ü | ü | ü | ü | ü | ü | ü | 30/11/2021
Priority Area 5.3: Improve awareness of personal safety and safeguarding
5.3.1 | Find out more about “Ask Angela” and the “Safe Places” national network initiatives. If we decide to adopt, produce an action and communication plan to include training and awareness within CCBC and look to promote this across the County. | Corporate Human Resources | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/12/2021
5.3.2 | Raise awareness of what are healthy relationships through the Spectrum project | Regulatory and Housing/ Safeguarding Managers | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
5.3.3 | The rights of people with learning disability to engage in relationships are recognised and we will work alongside Flintshire colleagues to support the re-establishment of a currently dormant regional co-production group focused on relationships and address the stigma around this issue, balancing that stigma with safeguarding concerns. | Social Care - Disability Service |  | ü | [7 empty] | 31/12/2020
5.3.4 | Continue to raise awareness of Telephone Fraud | Regulatory and Housing | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
5.3.5 | Working with partners, we will implement a plan to help prevent exploitation | Social Care – Children Families and Safeguarding | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/03/2022
5.3.6 | To promote and signpost parents and people of all ages to relevant resources which will enable them to stay safe on line | Social Care – Children Families and Safeguarding, | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/03/2022
5.3.7 | Safer Conwy to work with our third sector partners to support awareness raising and support the live fear free all Wales helpline. | Regulatory and Housing | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
5.3.8 | Work in partnership to reduce Anti Social Behaviour (ASB) | Regulatory and Housing | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
5.3.9 | Work in partnership to reduce crime and disorder in Conwy and Denbighshire by reducing incidents of victim based crime and Anti-Social Behaviour (ASB) for victims and perpetrators | Regulatory and Housing | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
5.3.10 | Work in partnership to reduce victim based crime | Regulatory and Housing | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
5.3.11 | Reduce crime, anti social behaviour and ensure public safety with CCTV | Regulatory and Housing | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
5.3.12 | Support vulnerable people to prevent them becoming victims of crime | Regulatory and Housing | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
5.3.13 | Provide target hardening to vulnerable people, when victims or vulnerable people are identified | Regulatory and Housing | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
5.3.14 | To work in partnership to reduce youth offending and adult offending | Regulatory and Housing | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
5.3.15 | Continue to work with our partners through the Community Safety Partnership to promote and sustain the fact that Conwy is a safe county. | Regulatory and Housing | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Objective 6 : Increase Access to Participation and improve diversity in decision making
Priority Area 6.1: Increase awareness of the importance of diversity in political representation and decision making bodies
6.1.1 | Whilst diversity data is collected from all candidates at elections by Welsh Government, we will locally seek to collect equality monitoring data as part of the induction for locally elected councillors and report on this with our Annual Employment Monitoring Reports | Law and Governance | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/12/2022
6.1.2 | Support diversity in democracy programme as appropriate | Law and Governance | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2021-12-31
6.1.3 | Produce a guide for recruiters on the use of positive action in the recruitment process | Corporate Human Resources | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2020-12-31
6.1.4 | Consider the use of positive action where appropriate | All Services | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2021 onwards
6.1.5 | Review the HM Government Public Appointments Diversity Action Plan 2019 to consider what good practice we can adopt locally that is relevant to us in our recruitment process | Corporate Human Resources | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/12/2022
6.1.6 | Co-option onto Council committees will be considered where permissible and appropriate to ensure a diverse balance of the committee. Member champions representing carers, older people, mental health, disability as well as the Modernisation portfolio holder covering Equalities, will be consulted as part of the normal decision making process | Law and Governance | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
6.1.7 | We will continue to develop the role of School Councils to ensure the voice of children and young people are heard | Education | ü | ü | ü | ü | ü | ü | ü |  | ü | Ongoing
6.1.8 | We will continue to develop the role of Conwy’s Youth Council to ensure the voices of young people are heard | Education | ü | ü | ü | ü | ü | ü | ü |  | ü | Ongoing
6.1.9 | North Wales Carers Strategy: Agencies designed to give carers a voice in local decision making and make sure all services in the area become more carer-aware and carer-friendly | Social Care (North Wales Carers Strategy) | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
6.1.10 | We will work with schools on citizenship and associate pupil governors providing training and support | Education | ü | ü | ü | ü | ü | ü | ü |  | ü | Review 31/8/2020
Priority Area 6.2 : Public transport providers* to provide training to staff to ensure they meet the needs of disabled people (*Note: Conwy County Borough Council does not provide public transport but is involved in some non-commercial routes and community transport)
6.2.1 | Deliver sustainable transport initiatives Service, digitising of bus including consideration of E-bikes, Electric Charging Points, Prescription Delivery timetables to real time | Community Development Services | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/3/2021
6.2.2 | We will review our support for taxis licenced by Conwy Council as part of the all-Wales review to take into account the recommendations for standard vehicles, conditions and training | Regulatory & Housing | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/12/2021
6.2.3 | We will consider how we will continue to deliver services for schools and community transport in the longer term with the changes to legislation affecting accessibility regulations of buses | ERF / Education / Social Care | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2021-03-31
6.2.4 | Participate in a pilot of an alternative public bus provision in North Wales | Environment, Roads & Facilities | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2020-07-31
6.2.5 | We will ensure all contracts with Conwy Council when renegotiated for Non-commercial bus routes (this covers less than 10% of all routes) will have a requirement within the grant to encourage providers to train staff around disability access | Environment, Roads & Facilities | ü | ü | ü | ü | ü | ü | ü | ü | ü | From 1/4/2020 and ongoing
6.2.6 | Work with communities, transport providers and other partners to undertake a fundamental review of transporting the public and access to services and we will pilot innovative alternative options | Environment, Roads & Facilities | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/3/2022
Priority Area 6.3: Ensure engagement is inclusive
6.3.1 | Promote training on engagement and consultation ensuring that our engagement process is inclusive and includes older people in care homes as well as children and young people who can often be overlooked | Corporate Improvement & Development | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
6.3.2 | Consider options for how to involve the public in undertaking Equality Impact Assessments on large scale proposals as part of the Equality Impact Assessment Policy review and whether a bespoke group should be formed which could act as an independent consultative and advisory group | Corporate Human Resources | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/12/2020
6.3.3 | Review the engagement with local disability forums. Consultation to focus on people in general, not just service users | Social Care |  | ü |  |  |  | ü |  |  |  | 31/12/2020
6.3.4 | Continue to Support the national and local digital inclusion agendas, eg, commissioning work to look at the exploitation of Digital Technology Opportunities for the rural area of Conwy and seek funding from Welsh Government for Wi-Fi infrastructure | Community Development Services | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
6.3.5 | Through the Conwy Welsh Language Strategy & Welsh Education Strategy we will encourage learning and speaking Welsh as a part of everyday life | All Services | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
6.3.6 | Continue to work towards closing gaps in the data we collect within all our services by protected characteristic | All services | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
6.3.7 | To develop a Communication user guide | Corporate Communications and Marketing | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
Priority Area 6.4: Access to services should be supported by appropriate language support
6.4.1 | Develop a Policy to reflect the checklist outlined in the Wales Audit Office audit (WAO) audit report "Speak My Language" | Corporate Improvement & Development | ü | [8 empty] | 2020-03-31
6.4.2 | Continue the provision of BSL interpreter real-time service | Community Development Services |  | ü | [7 empty] | Ongoing
6.4.3 | Review Big Word provision and consider potential alternatives to providing translation facilities to improve quality of translation service for languages other than Welsh and English including for migrants, refugees and asylum seekers | Corporate Human Resources | ü | ü | [7 empty] | 2020-12-31
6.4.4 | Ensure that services commissioned by the council (where appropriate) take account the needs of the deaf community/ equality of access | All Services |  | ü | [7 empty] | Ongoing
6.4.5 | Through the Conwy Welsh Language Strategy & Welsh Education Strategy we will encourage learning and speaking Welsh as a part of everyday life | Education | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2022-03-31
6.4.6 | Promote opportunities to encourage staff to take up part-time courses in British Sign Language in partnership with Llandrillo College | Corporate Human Resources | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2022-12-31
6.4.7 | Continue to run regular Sensory Impairment Awareness training and promote to front line staff | Corporate Human Resources |  | ü | [7 empty] | 2021-12-31
6.4.8 | Create a database to record all staff with BSL skills and to what level | Corporate Improvement & Development |  | ü | [7 empty] | 31/12/2021
6.4.9 | Implement standard wording on correspondence regarding how to receive information in alternative formats (and where services can access them) | CIDT / Corporate HR / Marketing | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2021-12-31
6.3.10 | Implement the new model of English as an Additional Language service delivery to Conwy schools | Education | ü | [8 empty] | 2020-12-31
6.4.11 | Contribute to Conwy's Phase 2 response to the welcoming families under the Home Office Syrian Vulnerable Persons Relocation Scheme | Education | ü | [8 empty] | 2020-12-31
Priority Area 6.5: Other actions on Participation and diversity in decision making identified from consultation
6.5.1 | Commence delivery of the Culture Strategy to embed Culture in strategy and planning; Guide, inform and inspire planning and investment over the 10 year period; Support and guide existing place-making, regeneration plans and strategies; Increase recognition of the financial and social value of the county’s cultural sector; and increase coordination and strengthen capacity for attracting funding, including large scale cultural investment bids | Community Development Services | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
6.5.2 | Upgrade the Website to reflect legislation to improve accessibility | Information Technology | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2020-12-31
6.5.3 | Improve the information available to parents using the Home to School transport service | Environment, Roads & Facilities | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing annually
6.5.4 | Develop a corporate policy on building repair and maintenance including the need to ensure appropriate access issues are catered for | Environment, Roads & Facilities | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2021-03-31
6.5.5 | Public Convenience Upgrades | Environment, Roads & Facilities | ü | ü | ü | ü | ü | ü | ü | ü | ü | 2020-12-31
Objective 7 : Develop our knowledge and understanding of the socio-economic duty (when guidance becomes available) to identify the key areas of impact to be addressed under each of our other 6 objectives
Priority Area 7.1: Initial actions identified from consultation
7.1.1 | Develop our knowledge and understanding of the socio-economic duty and communicate to services to ensure they understand what it means to them in delivering their services and meeting this duty | Corporate Human Resources | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/12/2020
7.1.2 | Raise awareness of ability to claim for housing benefit and council tax benefit on-line and for landlords to access benefit data via the web | Revenues & Benefits | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/12/2020
7.1.3 | Review Equality Impact Assessment Policy and develop it further to encompass how we can assess the socio-economic and cumulative impact on our decisions, policies and practices | Corporate Human Resources | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/12/2020
7.1.4 | Ensure when delivering our Events Strategy that we will offer a wide range of free events and activities which cater for the whole population | Marketing | ü | ü | ü | ü | ü | ü | ü | ü | ü | Ongoing
7.1.5 | Deliver the Economic Growth Strategy which includes a Higher Education presence; improving night time economy and winter tourism; tidal lagoon and renewable energy; State of the art business premises to encourage major economic development; Protection of employment land to improve the local economy | Community Development Services | ü | ü | ü | ü | ü | ü | ü | ü | ü | 21/12/2027
7.1.6 | Deliver the Colwyn Bay Town Centre Investment Plan | Venue Cymru | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/3/2021
7.1.7 | Develop and deliver an action plan to deliver the Destination Conwy Management Plan making Conwy a sustainable and buoyant tourist destination | Community Development Services | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/3/2029
7.1.8 | Review Equality & Diversity Policy to take into account the socio-economic duty and any other legislative changes once clear | Corporate Human Resources | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/12/20
7.1.9 | Contribute to the implementation of the recommendations from the Childcare Sufficiency Assessment action plan ensuring provision of childcare to enable parents to work. | Community Development Services | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/03/2022
7.1.10 | Build equalities into audit programmes across all 7 Equality Objectives to test this is being embedded and actions are undertaken | Audit & Procurement | ü | ü | ü | ü | ü | ü | ü | ü | ü | 31/12/2020